# Agency Board meeting

## 24 February 2026

## Quarter 3 financial monitoring report for period ending 31 December 2025

Purpose: This report is to provide an update to the Board on the following areas:

- Overall financial position

This is the third quarter financial report for 2025/26. Actual financial results for period 6 (1 April 2025 to 31 December 2025) show SEPA forecasting a break-even position to the year-end. This break-even position accounts for the agreed pay award costs, the consequence of which has increased vacancy targets for each portfolio.

- Capital budget

The capital summary for the period ending 31 December 2025 is provided in section 4 of this report.

### Recommendations:

The Board is asked to note SEPA’s financial performance for the period ending 31 December 2025, which is based upon financial returns from portfolios.

Authors: Ian Bryce, Deputy Head of Finance; Rosaleen Burke, Head of Finance.

Corporate Leadership Team Sponsor: Angela Milloy, Chief Officer Finance, Modernisation and Digital.

Date: 16 February 2026

### Table 1: Year to date (YTD) actuals and full year forecast

| Income and expenditure account at 31December 2025 | Year to date actual £’000 | Year to date budget £'000 | Year to date variance £'000 | Forecast outturn £'000 | Annual budget £'000 | Forecast variance £'000 |
| --- | --- | --- | --- | --- | --- | --- |
| Grant in Aid | 27,000 | 27,000 | 0 | 53,721 | 53,721 | 0 |
| Charging Schemes | 53,127 | 53,782 | (655) | 56,651 | 56,917 | (266) |
| Other income | 1,298 | 517 | 781 | 2,030 | 1,549 | 481 |
| Total income | 81,425 | 81,299 | 126 | 112,402 | 112,187 | 215 |
| Staff costs | 56,154 | 55,569 | (585) | 75,736 | 75,438 | (298) |
| Other staff costs | 1,200 | 748 | (452) | 1,482 | 950 | (532) |
| Transport costs | 644 | 709 | 65 | 941 | 1,061 | 120 |
| Supplies & services | 10,971 | 11,025 | 54 | 22,162 | 22,808 | 646 |
| Property costs | 3,430 | 3,514 | 84 | 4,602 | 4,550 | (52) |
| Depreciation/impairment | 5,535 | 5,535 | 0 | 7,479 | 7,380 | (99) |
| Total operating costs | 77,934 | 77,100 | (834) | 112,402 | 112,187 | (215) |
| Operating surplus/ (deficit) | 3,491 | 4,199 | (708) | 0 | 0 | 0 |

### Introduction

  - At period 9, variances are £0.7m- additional expenditure of £0.8m has been offset by additional income for £0.1m.

  - Net results for the full year report a balanced forecast.

### Total income - £112.4m

  - Total income for the full year is forecast at £112.4m, which is £0.2m more than full year budget.

#### Charging Scheme income - £56.7m

  - The full year charging scheme income forecast outturn at end December is £56.7m, which is £0.3m lower than budget.

  - The net variance includes:

- Applications: £0.1m positive variance in the applications forecast. This is due to an increase in waste applications offset by decreases across other media.

- Subsistence: £0.4m negative variance in the subsistence forecast. This variance is mainly due to reduced income across all media.

#### Graph 1: Charging Schemes by media

Note: Graph 2 acronym: RSA – Radioactive Substances Activity

#### Other income - £2m

  - The full year other income forecast outturn is £2m, being £0.5m higher than the budget, mainly due to monies being returned to SEPA as result of unspent grants.

#### Revenue Grant in Aid (GiA) - £53.5m

#### Table 2: Grant in Aid

|  | Resource budget cash £’000s | Resource budget non- cash £’000s | Total £’000s |
| --- | --- | --- | --- |
| Base budget allocation 2025/26 | 42,400 | 7,377 | 49,777 |
| Budget adjustments |  |  |  |
| Regulation systems | 995 |  | 995 |
| Multi agency fish farm consenting | 261 |  | 261 |
| Water Environment Fund | 1,887 |  | 1,887 |
| Flood Advisory Service | 150 |  | 150 |
| Cleaner Air (CAFS 2) | 30 |  | 30 |
| Air Quality (Volcanic Monitoring) | 28 |  | 28 |
| Air Quality (Zephyre Maintenance) | 12 |  | 12 |
| Emission Trading Scheme & Fgas | 331 |  | 331 |
| Water Environment Fund - SBR | 250 |  | 250 |
| Total adjustments | 3,944 | 0 | 3,944 |
| Total revenue budget | 46,344 | 7,377 | 53,721 |

  - Revenue GiA for 2025/26 has increased by £3.9m since budget set following additional funds for WEF work, regulation systems, fish farm consenting and flood advisory service. The additional funds for fish farm consents and regulation monies were awarded following successful applications to Scottish Governments Public Service Reform (PSR) Invest to Save Fund.

### Total revenue expenditure - £112.4m

  - Full year operating costs are forecast to be £0.2m more than budget. The graph below provides a detailed breakdown by expenditure type.

Graph 2: Expenditure by type

#### Staff costs

  - Budgeted staff costs represent 67% of total expenditure. The full year forecast for staff costs is £0.3m above budget; £0.9m lower than budgeted vacancy management savings are offset by £0.5m reduction in corporate costs.

#### Other staff costs

  - Other staff costs are currently forecasting an overspend of £0.5m mainly due to higher than budget forecast expenditure for temporary workers and recruitment costs. These costs are generally funded from vacancy savings, however with targets not currently being achieved they are funded from underspends in corporate costs.

#### Transport costs

  - Transport costs are forecast to have a full year underspend of £0.01m. This is the net movement due to reduced mileage claims primarily due to improved fleet provision.

#### Supplies and services

  - The full year forecast for supplies and services is currently reporting a forecast underspend of £0.6m. The underspend relates to budget movements between non-staff and staff expenditure lines to fund the pay award and potential in year budget pressures within some portfolios.

#### Property costs

  - The full year forecast for property costs is currently reporting an overspend of £0.05m, which mostly relates to overspends on maintenance.

### Capital expenditure summary

  - SEPA’s capital budget provided by Scottish Government for the year is £5.64m. In year, SG confirmed funds of an additional £0.6m to support the creation of a foundational flood and coastal asset database for Scotland and £1m for wave buoy deployment, increasing the total capital budget to £7.21m.

  - The base budget was approved with an over commitment based on the historical knowledge that capital projects are liable to delays, slippage of spend or revision of original budget estimates during the procurement journey. The current expenditure forecast is £0.3m below budget.

#### Table 3: Capital budget 2025/26

| Function | Budget £'000 | Forecast £'000 | Main projects within function budgets |
| --- | --- | --- | --- |
| Digital Transformation | 495 | 30 | Compliance Project |
| Governance | 1,450 | 181 | Digital Data Architecture |
| Chemistry | 124 | 400 | Nutrients Analysers & Lab Balances |
| Environmental quality | 93 | 86 | Bathing Waters Signage |
| Info Systems | 250 | 470 | High Performance Computing & Laptop Replacement |
| Info Systems (Digital) | 1,150 | 1,220 | Integrated Authorisation Framework Implementation |
| People Systems | 70 | 60 | Applicant Tracking System |
| Finance Systems | 50 | 46 | Charging Cost Review |
| Workspaces | 1,045 | 1,674 | Stirling Office Dilapidations & Fleet Replacement |
| Hydrology | 3,466 | 2,761 | Gauging Stations & Flooding projects, flood & coastal asset database and wave buoy deployment |
| Savings to be identified | (983) | 0 |  |
| Totals | 7,210 | 6,928 |  |

  - At the end of period 9, there are 69 live projects with the focus this year being the design phase of SEPA’s digital transformation, flood and hydrology, the continuation of the integrated authorisation framework system and work related to estates, especially the Stirling office.

### Statement of financial position

  - The Statement of financial position is provided over the page.

#### Table 4: Statement of financial position

| Statement of financial position | Period to December 2025 £'000 | Year to March 2025 £'000 |
| --- | --- | --- |
| Non-current assets |  |  |
| Property, plant and equipment | 37,038 | 42,075 |
| Intangible assets | 3,529 | 4,027 |
| Assets under construction | 2,380 | 2,380 |
| Employee retirement benefits | 0 | 0 |
| Trade and other receivables | 232 | 232 |
| Total non-current assets | 43,179 | 48,714 |
| Current assets |  |  |
| Trade and other receivables | 5,374 | 5,029 |
| Cash and cash equivalents | 5,188 | 2,346 |
| Total current assets | 10,562 | 7,375 |
| Total assets | 53,741 | 56,089 |
| Current liabilities |  |  |
| Trade and other payables | (9,285) | (13,683) |
| Provisions | (231) | (231) |
| Future lease payments | (1,306) | (1,306) |
| Total current liabilities | (10,822) | (15,220) |
| Total assets less current liabilities | 42,919 | 40,869 |
| Non current liabilities |  |  |
| Provisions for liabilities and charges >1 year | (6,059) | (6,059) |
| Future lease payments | (5,475) | (5,475) |
| Total non-current liabilities | (11,534) | (11,534) |
| Total assets less total liabilities | 31,385 | 29,335 |
| Taxpayers' equity and other reserves |  |  |
| General fund | 12,345 | 10,295 |
| Revaluation reserve | 19,040 | 19,040 |
| Total tax payers’ equity | 31,385 | 29,335 |

### Recommendation

  - The Board is asked to note SEPA’s financial performance for the period ending 31 December 2025, which is based upon financial returns from portfolios.

END

<Report date here (month, year)>