November 2025

Quarter 2 2025-2026

Corporate Performance Summary Report

# Contents

Contents	1

1. Executive Summary	3

Key highlights	3

Exceptions and recovery	4

2. Performance Summary	6

2.1 Annual Objectives and Key Results (OKRs) – Progress and exception summary	8

2.2 Key strategic and operational performance indicators – Progress and exception summary	11

3.	Performance Updates	23

Net Zero	24

Climate Resilience	28

Water Environment	34

Resource Efficiency	40

Business Environmental Performance	43

Our Organisation	50

If you would like this document in an accessible format, such as large print, audio recording or braille, please contact SEPA by emailing: equalities@sepa.org.uk.

# 1. 	Executive Summary

This year’s Annual Operating Plan includes a suite of performance measures aligned to our corporate plan priorities. These aim to measure how we are fulfilling our long-term mission of protecting Scotland’s environment and communities, as well as how we are performing as an organisation overall. Our measures include:

- Annual objectives and key results (OKRs) which set out our clear, short-term areas of focus for us to target ambitious, measurable change and impact.

- Strategic and operational key performance indicators (KPIs) which provide a continuous view of our performance.

Each quarter we produce a report to explain how we are progressing with our measures.  This is the second quarterly report covering the period July 2025 to September 2025.

## Key highlights

Net zero

- We received 100% of requested energy efficiency data from energy intensive sites.

- Greenhouse gas emissions from all SEPA-regulated industrial facilities fell by 3.85% (0.37 megatonnes carbon dioxide equivalent) (CO2e), compared with 2023. This is continuing a long-term downward trend overall since 2007. The reduction is the equivalent of taking around 210,000 petrol cars off the road for a year.

- We launched the Climate Change Impact Assessment (CCIA) on time, a milestone due in Q2. This will be used to ensure climate impacts have been considered in relation to all strategic leadership decisions and regulated procurements.

- Our emissions from workspaces are down by 21% and from travel (excluding the Sir John Murray) are down by 11% against Q1 in our baseline year.  We also received delivery of an additional electric vehicle (EV) in July 2025, bringing the total number of EVs in the SEPA owned or leased fleet to 26.

Climate resilience

- We have completed the risk assessment database build to produce statistical output for the National Flood Risk Assessment.

- We responded to 96% of planning consultations within time, against an 80% target.

Resource Efficiency

- We launched our baseline survey of Scotland’s businesses to assess awareness of the UK digital waste tracking service.

Business Environmental Performance

- We successfully completed an interventions framework to enhance our existing SEPA toolkit and improve partnership working.

- We achieved our targets to reduce the overall environmental risk score of identified illegal activities, including high risk sites, significantly earlier than planned - by Q2 instead of Q4. In light of this progress, new stretch targets will be introduced for Q3 onwards to sustain momentum and drive further improvement.

Our organisation and transformation

- We achieved our target of 50% of colleagues accessing leadership or personal development opportunities through e-learning, workshops and facilitated programmes, earlier than planned - Q2 instead of Q4.

- We are continuing to pay over 90% of all supplier invoices within 10 working days.

- Career role profiles have been fully launched (a milestone due in Q2), and our new careers site is live. Progress continues to be made on our employer brand, integrating our passionately purposeful wording into our online presence.

## Exceptions and recovery

Net zero

- Mileage of non-SEPA owned fleet vehicles has seen a 40% increase when comparing Q1 2024/25 to Q1 2025/26 data. Therefore, we are forecasting that a reduction in mileage of non-SEPA owned vehicles by 10% will not be delivered in 2025/26. A cross-organisation action plan is being developed to address this, which includes portfolio/team travel targets and fleet plans, using newly introduced telematics data to more effectively locate our fleet vehicles where needed, emphasising expected behaviours through our travel hierarchy and planning to review people policies later in 2026.

Water Environment

- There are risks around the delivery of the River Basin Management Plan (RBMP3) programme of actions to improve the water environment. These risks have been highlighted and delivery of RBMP3 targets has been discussed with the Corporate Leadership Team. Mitigation options are being considered. We are therefore forecasting partial delivery for Key Result 5.3 - 90% of our programme of actions for the water environment are delivered. We are focusing on tracking progress across key stages in the RBMP3 programme for the remainder of 2025/26.

Resource Efficiency

- We are continuing to pursue key results in our preparations to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government. This is an externally led, four-nations project run by DEFRA, and our confidence in delivery of this objective is influenced by the outcomes not entirely being within SEPA's control. We are forecasting partial delivery for the following key results:

  - 50% of SEPA’s requirements are incorporated into the UK digital waste tracking service (by the DEFRA digital build team) and is ready for testing by SEPA users (KR7.2).

  - SEPA is ready to support the introduction of the UK Digital Service by DEFRA for Scotland’s users in 2026 (KR7.3).

Our Organisation

- We have made significant progress developing SEPA's first Customer Experience Strategy. This will set an ambitious direction to transform our customer contact and engagement, while also aiming to deliver improvements that will build towards a sustainable and adaptable service such as enhancing technology and digital capability, addressing immediate priorities, and embedding service standards.

- We have commissioned external customer research to inform our strategy development, the results of which are expected by the end of this financial year. It is important we use the findings to inform the new digital contact methods (KR10.1) as well as the target service level agreement timeframes (KR10.3), to ensure these are future proof. As a result, we have taken the decision to pause these for now and review for 2026/27.

- This decision is considered and carries no associated risks. In the interim, our current customer hub remains fully resourced and continues to provide robust and effective support to businesses and the public.  We will proceed with completing the platform tender process in preparation for this to be delivered going forwards. We will also look to progress Customer Service Standards implementation (KR10.2) (excluding the new digital channels) through a test and learn approach. We will aim to have these implemented by the end of Q4 to align with the broader programme timeline and ensure that they are informed by accurate operational data.

We continue to develop our reporting mechanisms and style to enable effective scrutiny of our delivery in the upcoming period.

# 2. 	Performance Summary

This section provides a high-level, visual summary of the status of each OKR and KPI for quarter one.

Figure 1: Overall OKRs by status as at Q2. 				   		Figure 2: Breakdown of overall OKRs by status and quarter.

(N=11)

Figure 3: KPIs by status as at Q2.    				   			Figure 4: Breakdown of KPIs by status and quarter.

## 2.1 Annual Objectives and Key Results (OKRs) – Progress and exception summary

This section provides a summary of progress and any exception commentary for our OKRs as at Q2. Table 1 outlines the scoring matrix applied. We have also noted guidance to consider when reviewing the report.

Table 1: OKR scoring matrix

| Scoring | Status | Description |
| --- | --- | --- |
| 0.70 to 1.00 |  | Delivering – We are delivering or have delivered against our OKR measure this quarter. |
| 0.31 to 0.69 |  | Progressing – We are making measurable progress against delivery of our OKR measure this quarter but remain short of our target. |
| 0.00 to 0.30 |  | No progression – We did not make significant measurable progress towards delivery of our OKR measure this quarter. |
| Not applicable |  | Not started – Activity has not yet started or is not yet due for our OKR measure this quarter. |
| Not applicable |  | Complete – The OKR measure is complete and the deadline for completion has passed. |

Key results and Objectives Scoring Guidance

When reviewing the OKRs scoring in the report, please consider the guidance below:

Key results scores

- Key results are scored on a sliding scale between 0 and 1, with 1 representing 100% delivery.

- Key result scores are typically set to measure the desired outcomes, not actions or activity. The score therefore aims to show what has been delivered in the quarter in terms of quantifiable impact or change, not what activity may have been undertaken. As a result, a KR can be scored ‘0’ or N/A and still be on track for delivery by the due date.

- For example, let us assume we have a key result to ‘Replace 1000 monitoring stations by Q1’. If we replace 300 monitoring stations, the key result would be scored as 0.3. If we replace 950 monitoring stations, the key result would be scored as 0.95.

- As key results are designed to drive ambitious, stretch goals with measurable change and impact, any score over 0.70 is considered as delivering against the measure.

Overall objective score

- An overall objective score equates to the cumulative score of each key result, divided by the number of relevant key results.

- For example, assuming we have three KRs with scores provided, the calculation would be ‘KR1 score + KR2 score + KR3 score’ divided by three = Overall OKR score. If a key result is noted as not started, this is not included in the cumulative calculation.

Table 2: OKR progress and exception summary

| Code | Priority | Objectives | Q1 score | Q2 score | Q3 score | Q4 score | Status | Q2 Exception Commentary | Annual Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NZ OKR1 | Net Zero | Develop our regulatory role with a more integrated approach to energy efficiency and industrial decarbonisation. | 0 | 0.66 | - | - |  | Delivery on track. | Delivered |
| NZ OKR2 | Net Zero | Transform our workspaces and fleet to minimise emissions, reduce costs and move to co-located workspaces by default and zero emissions fleet by 2030. | 0.33 | 0.25 | - | - |  | We are on track for delivering three out of the four Key Results for this objective, with significant progress made. An action plan is to be implemented for Key Result 2.3. | Partial Delivery |
| CR OKR3 | Climate Resilience | Improve awareness and understanding of flood and drought risk, including implications of climate change, to support effective decision making. | 0.80 | 0.90 | - | - |  | Delivery on track. | Delivered |
| CR OKR4 | Climate Resilience | Ensure effective and resilient flood services which are designed to meet future requirements. | 0.50 | 0.50 | - | - |  | Delivery on track. | Delivered |
| WE OKR5 | Water Environment | Deliver River Basin Management Plan programme of actions to improve the water environment. | 0.35 | 0.47 | - | - |  | We are on track for delivering three of the four Key Results for this objective. | Partial Delivery |
| WE OKR6 | Water Environment | Prepare for future cycles of river basin management planning. | N/A | N/A | - | - |  | Delivery on track. All Key Results due from Q3 onwards. | Delivered |
| RE OKR7 | Resource Efficiency | Prepare to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government. | 0 | 0.50 | - | - |  | We are on track for delivering areas within our control. We continue to pursue clarity from DEFRA’s digital build team regarding SEPA’s requirements and what will be delivered by Q4. Until this is received, we are forecasting partial delivery. | Partial Delivery |
| BEP OKR8 | Business Environmental Performance | Ensure key stakeholders are engaged and informed on the necessary preparations required for compliance with the Biodegradable Municipal Waste (BMW) Landfill ban. | 0.33 | 0.33 | - | - |  | We remain on track with our preparations. Discussions between the Scottish Government and industry on readiness and the Energy from Waste (EfW) capacity gap are ongoing. Clarity on any potential amendments to the ban, aimed at addressing this gap, is expected from the Scottish Government by the end of October. | Delivered |
| BEP OKR9 | Business Environmental Performance | Tackle environmental crime using interventions approach. | 0.13 | 1 | - | - |  | The targets for Key Results 9.1 to 9.3 have already been reached. New stretch targets are to be implemented from Q3. Key Result 9.4 is not due to be delivered until Q4. | Delivered |
| OO OKR10 | Our Organisation | Introduce effective digital public contact services for customers. | N/A | 0 | - | - |  | We are awaiting results from externally commissioned customer research to inform our strategy development, which is expected by the end of this financial year. It is important we use the findings to inform the new digital contact methods (KR10.1) as well as the target service level agreement timeframes (KR10.3), to ensure these are future proof. As a result, we have decided to pause these for now and review them for 2026/27. We continue to progress Customer Service Standards implementation (KR10.2) (excluding the new digital channels) and now aim to have these in place by the end of Q4 to align with the broader programme timeline. | Partial Delivery |
| OO OKR11 | Our Organisation | Deliver our People Strategy to build a safe, welcoming and high performing environment which empowers our people to be purposeful, professional and passionate. | 0.58 | 0.66 | - | - |  | Delivery on track. | Delivered |

## 2.2 Key strategic and operational performance indicators – Progress and exception summary

A high-level summary of the progress of each key performance indicator aligned to our corporate plan priorities for quarter two is below.

Table 3: KPI progress and exception summary

| Code | Priority | Performance Indicator and Trajectory | Measure Type | Baseline | Target | Q2 Result | Q2 Status | Q2 Commentary | Annual Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NZ01 | Net Zero | Annual greenhouse gas emissions in the Scottish Pollutant Release Inventory– Reducing | Strategic – Indirect influence | Baseline provided from 2007 Scottish Pollutant Release Inventory (SPRI) | Publish SPRI on time and in accordance with the Code of Practice – SEPA responsibility. Reduce annual greenhouse gas emissions – National outcome for Scotland, SEPA plays a contributing role. | 2024 SPRI data published on time on 30 September 2025. 3.85% reduction in greenhouse gas emissions. | Achieved | Greenhouse gas emissions from all SEPA-regulated industrial facilities fell by 3.85% (0.37 megatonnes carbon dioxide equivalent) (CO2e), compared with 2023. This is continuing a long-term downward trend overall since 2007. The energy sector remained the highest emitting sector, with 38.6% of total industrial greenhouse gas emissions. However, energy sector emissions fell by 7.4% from 2023 to 2024 largely due to changes in production outputs. | Achieved |
| NZ02 | Net Zero | Annual reports of greenhouse gas emission by SEPA - Reducing | Strategic – Direct Control | 1742 tCO2e in 2022/23 | Reduce direct emissions by 15% by March 2026 - Target: 1481 tCO2e. | 506.8 tCO2e | Partially Achieving | Progress against this KPI is reported one quarter in arrears. Total emissions in Q1 were 506.8 tCO2e. This represents a 9.3% increase in our total emissions against our Q1 2022/23 baseline. This result is entirely due to increase in emissions from the Sir John Murray (SJM) survey vessel which travelled to Hull for a refit during this time. SJM emissions were 172 tCO2e in Q1 this year compared to 54.49 tCO2e Q1 baseline. The increased emissions from SJM masks positive performance in other areas. Emissions from workspaces are down by 21% and from travel (excluding SJM) are down by 11% against Q1 in our baseline year. | Partially Achieved |
| NZ03 | Net Zero | Percentage of vehicles in SEPA fleet that are zero emissions - Increasing | Operational – Direct control | 25 EVs in SEPA’s fleet as of 1 April 2025 | 26 EVs in SEPA fleet as a minimum by 31 March 2026 | 26 EVs | Achieved | We received delivery of an additional electric vehicle (EV) in July 2025, bringing the total number of EVs in the fleet to 26. | Achieved |
| NZ04 | Net Zero | Number of SEPA solely owned or leased buildings - Reducing | Operational – Direct Control | 11 buildings solely owned or leased by SEPA as of 1 April 2025 | Reduction of 2 workspaces per annum. | 11 | Partially Achieving | We have made positive progress to exit two workspaces earlier than anticipated. We expect to achieve this KPI target in Q3. | Achieved |
| CR01 | Climate Resilience | Number of flood warnings and alerts issued by SEPA - Maintaining | Strategic – Direct control | Average number of alerts (244) and warnings (342) issued on an annual basis calculated over the last 14 financial years. | Maintain - The number of reports and warnings is dependent on the duration of a flood event and associated conditions. | 66 regional flood alerts 25 local flood warnings. | Achieving | Cumulative total for the year is 84 regional flood alerts and 28 local flood warnings. The period was marked by several periods of localised heavy intense rainfall resulting in localised flooding impacts, for example in Perthshire and Scottish Borders on 22-25 July. There was also a coastal event during Storm Floris on 3-5 August affecting mainly the north and west of Scotland. | Achieved |
| CR02 | Climate Resilience | Number of water scarcity warnings and alerts issued by SEPA - Maintaining | Strategic – Direct control | 23 x weekly water scarcity reports 1 x autumn water and 1 x winter water situation report. 914 normal conditions. 152 early warning. 12 alert. 1 moderate scarcity. Nil significant scarcity. | Maintain - The number of reports and alerts/ warnings is dependent on the duration of a water scarcity event and associated conditions. | 13 weekly reports issued. 312 normal conditions. 118 early warning. 64 alert. 101 moderate. 49 significant scarcity. | Achieving | Cumulative total for the year is 24 weekly reports issued: with the following break down on water scarcity levels: 382 Normal, 328 Early Warning, 223 Alert, 179 Moderate, 50 Significant. There continued to be an increase in the number of warnings and alerts because of prolonged conditions associated with water scarcity. Parts of the east coast have been at significant alert level across the whole period. | Achieved |
| CR03 | Climate Resilience | Percentage of daily Flood Guidance Statements and Scottish Flood Forecasts issued on time ​- Maintaining | Operational – Direct control | 2023/24 84% by 10:30 98% by 11:00 | At least 84% of Flood Guidance Statements are issued by 10:30am and 98% by 11:00am. The Scottish Flood Forecast is published at the same time. | 91.3% of the Flood Guidance Statements were issued by 10:30. 100% of Flood Guidance Statements were issued by 11:00 | Achieving | Cumulative progress at Q2 ahead of target: - 93.4% Flood Guidance Statements issued by 10:30 - 99.5% Flood Guidance Statements were issued by 11:00 | Achieved |
| CR04 | Climate Resilience | Percentage of water scarcity warnings and alerts issued on time - Maintaining | Operational – Direct control | No baseline, first year of reporting. 2025/26 will establish the baseline. | Water Scarcity reports published on Thursdays by 15:00. 100% of messages to abstractors as a result of changes to locations status in relation to Water Scarcity level sent by Friday 15:00. | 100% | Achieving | 100% performance maintained from Q1. All identified authorisation holders whose activities are affected by water scarcity and who have supplied up to date contact information to SEPA, received the appropriate Water Scarcity level advice within 24 hours of the Water Scarcity Report being made public. All new and reviewed contact details are updated as required. Total number of communications sent: - Q1: 5960 - Q2: 4900 | Achieved |
| CR05 | Climate Resilience | Number of people accessing flood warning information on SEPA’s website ​- Maintaining | Operational – Direct control | 896,038 annual users accessing SEPA flood forecasting and warning services web pages. Baseline derived using data from 1 January 2024 – 31 December 2024 | Maintaining – The number of users will be dependent on the duration of a flood event and associated conditions. | 110,631 views | Partially Achieving | Cumulative total for year is 169,864 views of SEPA flood forecasting and warning services web pages. Q2 result is nearly double compared to Q1 but remains significantly lower compared to last year’s annual total (12.3%). Lower views likely due to the relatively limited flood warning activity during the quarter (see CR01), so limited incentive for people to seek our information. | Achieved |
| CR06 | Climate Resilience | Percentage of new developments approved in accordance with SEPA's advice on flood risk – Maintaining | Strategic – Direct Influence | 98.4% 2024/25 baseline. 1478 consultations on 946 separate planning applications. | Maintain >95%, recognising that exceptions may occur. | 97.3% of 292 consultations | Achieving | Eight developments were approved against SEPA’s advice this quarter, following notification to Scottish Ministers. Cumulative Q1 and Q2 performance: 98.02% | Achieved |
| CR07 | Climate Resilience | Percentage of responses to planning consultations within time​ - Increasing | Operational – Direct control | 70% 2023/24 baseline | Increase the percentage of consultations responded to within time to over 80%. | 91.4% | Achieving | Performance for Q2 is 91.4%. We responded to 522 planning consultations on time with 49 responses beyond time. Cumulative Q1 and Q2 performance to date is 87.5%. 1158 on time, 145 beyond time. Please note there was an error in the previously reported Q1 figure of 90%. This was due to auditing underlying data and determining some information had not been completed. The revised figure for Q1 is 86.9%. 636 consultations on time, 96 beyond time. | Achieved |
| CR08 | Climate Resilience | Number of people registered to Floodline to receive flood alerts and warnings – Increasing | Operational – Direct Influence | 41,992 registrations at the end of March 2025 | An increase from 41,992 registrations by the end of March 2026 | 41,770 registrations | Partially Achieving | We had a net increase of 6 registrations to Floodline compared to Q1. 521 new registrations offset with 515 deregistrations. We know that new registrations are usually highly correlated to significant flood events which thankfully have been limited so far this year but are more likely as we move into the winter months. From Q3, we are planning to promote the Floodline service for “winter readiness” across SEPA channels including our newsletter, social media, media releases and internally. We will also send an annual reminder message to existing customers to confirm that their details are up to date. We would expect to see a net increase in registrations in the second half of the year. | Partially Achieved |
| WE01 | Water Environment | Classification of water bodies across Scotland - Increasing | Strategic – Direct Influence | 2020 data (start of third RBMP) Good or better overall condition = 66% | National outcome for Scotland and SEPA plays a contributing role As set out in RBMP3: Good or better overall condition = 81% by 2027 | Not Applicable | Not Applicable | This figure will be available when Classification 2024 is released. This is on track, and the report is in the final stages of governance review. | Achieved |
| WE02 | Water Environment | Number of water bodies at High, Good, Moderate, Poor or Bad status/potential​ for water quality. – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP) Good or better overall condition = 87% | As set out in RBMP3: Good or better overall condition = 92% by 2027 | Not Applicable | Not Applicable | This figure will be available when Classification 2024 is released. This is on track, and the report is in the final stages of governance review. | Achieved |
| WE03 | Water Environment | Number of water bodies at High, Good, Moderate, Poor or Bad status/potential​ for water flows and levels – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 90% | As set out in RBMP3: Good or better overall condition = 96% by 2027 | Not Applicable | Not Applicable | This figure will be available when Classification 2024 is released. This is on track, and the report is in the final stages of governance review. | Achieved |
| WE04 | Water Environment | Number of surface water bodies at High, Good, Moderate, Poor or Bad status/potential​ for physical condition. – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 90% | As set out in RBMP3: Good or better overall condition = 92% by 2027 | Not Applicable | Not Applicable | This figure will be available when Classification 2024 is released. This is on track, and the report is in the final stages of governance review. | Achieved |
| WE05 | Water Environment | Number of surface water bodies at High, Good, Moderate, Poor or Bad status/potential​ for fish migration – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 88% | As set out in RBMP3: Good or better overall condition = 99% by 2027 | Not Applicable | Not Applicable | This figure will be available when Classification 2024 is released. This is on track, and the report is in the final stages of governance review. | Achieved |
| WE06 | Water Environment | Percentage of bathing waters meeting excellent, good, or sufficient quality standards​– Improvement | Strategic – Direct Influence | 2024/2025 baseline classification 89 bathing waters with 96.6% sufficient or better | Achieving - the percentage of bathing waters at excellent, good and sufficient classifications to meet or exceed the baseline percentage. | Not Applicable | Not Applicable | The 2025/2026 bathing water classifications have now been calculated and will be available for public release on 18 November 2025. There are no red flags currently that indicate a serious degradation. | Achieved |
| RE01 | Resource Efficiency | Rates of waste to landfill in annual Scottish household waste data - Reducing | Strategic – Indirect influence | 2011 data (1.45 million tonnes of Scottish household waste landfilled) | Rates of waste to landfill to decrease – National outcome for Scotland and SEPA plays a contributing role. Publish Scottish household waste data on time and in accordance with the Code of Practice – SEPA responsibility. | Not Applicable | Not Applicable | All work currently on track for the publication date of the 2024 Official Statistics report on 28 October 2025. Pre-release of the Official Statistics was issued on time on 21 October 2025. | Achieved |
| BEP01 | Business Environmental Performance | Number of successful interventions per year – Increasing | Strategic – Direct Influence | 2024/25 baseline: 167 interventions. | Increasing number of interventions | 48 interventions | Achieving | Total of 125 interventions by Q2: - Q1 – 77 interventions. - Q2 – 48 interventions We have increased the number of interventions in comparison to Q2 2024-2025 (106 interventions). We expect this will increase further as the interventions framework is implemented by end of Q4. | Achieved |
| BEP02 | Business Environmental Performance | Percentage of environmental monitoring statutory reports published by the scheduled date – Maintaining | Operational – Direct control | 2024/25 baseline – 100% Four out of four on-time publication rate from the previous year. | 100% - Four out of four reports published on-time | No reports published this quarter. | Achieving | Reports progressing. Annual Bathing Water and Water environment Classifications reports are expected to be published in Q3. The two Bathing Waters statutory reports were published on time during Q1 for the 2025 bathing water season (Bathing Water profiles and Bathing Waters locations details) but not reported. | Achieved |
| BEP03 | Business Environmental Performance | Percentage of statutory reviews completed – Increasing | Operational – Direct control | 2024/25 baseline 31% | 80% of in scope planned permit reviews and variations by year end (39 Best Available Techniques (BAT) conclusions / 13 medium combustion plant permit variations) | 10 permits – 19.2% (cumulative by Q2) | Achieving | The Q2 target is 25% of statutory reviews complete which equates to 13 of the in-scope permits. 10 permit variations have been issued which is within the 10% (5 permit) tolerance hence the Q2 status being shown as 'Achieving'. | Achieved |
| BEP04 | Business Environmental Performance | Percentage of applications determined within statutory determination times – Increasing | Operational – Direct control | 2023/24 baseline: 92% all applications 75% for permitting licences / 87% for permitting registrations | Maintain the percentage of applications determined within statutory timelines. | 90% of all applications 70% for permitting licences / 98% for permitting registrations | Partially Achieving | Due to resource pressures we are partially achieving with Q2 statistics showing 90% of all applications determined within statutory determination times. The main reason for this slight reduction is due to long standing applications for permitting licenses being determined. We are maintaining high performance for permitting registrations. | Partially Achieved |

# Performance Updates

## Net Zero

Our ambition is to fully play our part in helping Scotland become a net zero country by 2045 and reduce our own emissions towards net zero.

### NZ OKR01: Develop our regulatory role with a more integrated approach to energy efficiency and industrial decarbonisation.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR1.1: 100% of requested energy efficiency data received from energy intensive sites. | Q2 | 0 | 1 | - | - |  | Key result complete in Q2. We received 100% of requested information. | Delivered |
| KR1.2: Direct engagement with three pilot sites, from the list of energy intensive sites. | Q3 | N/A | 0.33 | - | - |  | We engaged the Outcome Based Collaborative Regulation (OBCR) site. The other two sites will be engaged once the evidence-based pilot site selection is complete. Confidence in forecast: High | Delivered |
| KR1.3: Deliver options assessment of regulatory approaches in relation to energy efficiency and industrial decarbonisation. | Q4 | N/A | N/A | - | - |  | We will develop the results and options of our work with the pilot sites in Q4. We will report to the Regulation, Business and Environment Management Team at the end of Q4. Confidence in forecast: High | Delivered |

Q2 Overall objective score = 0.66

### NZ OKR02: Transform our workspaces and fleet to minimise emissions, reduce costs and move to co-located workspaces by default and zero emissions fleet by 2030.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 2.1: Launch strategic approach to our Fleet, working to reduce emissions in our owned vehicle fleet. | Q1 | 1 | 1 | - | - |  | Key result delivered in Q1. | Delivered |
| KR 2.2 100% of all business travel by fleet vehicles is tracked. | Q3 | 0 | 0 | - | - |  | Contract awarded and being mobilised. Currently on track for delivery Q3, subject to key dependencies including Data Protection Impact Assessment, publication of Driving for Work Policy and the Change & Control Board (CaCB). Confidence in forecast: Moderate | Delivered |
| KR 2.3: Reduce mileage of non-SEPA owned fleet vehicles by 10%. | Q4 | N/A | 0 | - | - |  | Reporting on this Key Result is one quarter in arrears. Q1 data shows a 40% increase from Q1 2024/25. Cross-organisation action plan being developed to address. Low confidence in 10% annual reduction against 2024/25 baseline, which is reflected in the annual forecast. | Not Delivered |
| KR 2.4: 5% reduction of greenhouse gas emissions from SEPA workspaces by realising savings through workspaces transformation. | Q4 | 0 | 0 | - | - |  | Progress on track. Glasgow exit progressing and negotiations continuing positively on early Stirling lease exit. Confidence in forecast: High | Delivered |

Overall objective score = 0.25

## Climate Resilience

Our ambition is that the damaging impacts of floods and droughts is reduced, and that operators are prepared for and resilient to the impacts of a changing climate.

### CR OKR3: Improve awareness and understanding of flood and drought risk, including implications of climate change, to support effective decision making.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 3.1: Complete risk assessment database build to produce statistical output for flood risk assessment service reporting. | Q2 | 0.80 | 0.90 | - | - |  | Key result delivered. Skeleton database build complete. We are awaiting completion of quality control checks to confirm that the database is functioning as expected prior to fully scoring 1.0. | Delivered |
| KR 3.2: Publish a revised National Flood Risk Assessment for Scotland by 31 December 2025. | Q3 | N/A | N/A | - | - |  | On track for publication by 31 December 2025. Confidence in forecast: High | Delivered |
| KR 3.3: Engage five national utility infrastructure owners to increase awareness of the potential wider impacts of flooding. | Q4 | N/A | N/A | - | - |  | Key result is dependent on delivery of KR3.2, so will be progressed in Q4 onwards, subject to availability of stakeholders. Confidence in forecast: Moderate | Delivered |
| KR 3.4: All irrigation licences varied to include a time limited water scarcity condition. | Q4 | N/A | N/A | - | - |  | On track. Currently contacting all licence holders and have a project plan in place to deliver on schedule. Confidence in forecast: High | Delivered |

Overall objective score = 0.90

### CR OKR4: Ensure effective and resilient flood services which are designed to meet future requirements.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR4.1: Review all 10 flood services to identify improvements and future design requirements | Q2 | 0.70 | 0.70 | - | - |  | On track. Dependency on Digital Design Partners being onboarded. Confidence in forecast: Moderate to High | Delivered |
| KR 4.2: Increase the number of stations that deliver hydrometry data in near real time (within 30 minutes) from 70% to 95%. | Q4 | N/A | N/A | - | - |  | Work due to commence in Q4 onwards. The improvement in data latency (the time between data generation and when it is available for use) depends on the roll out of new data loggers. The data loggers cannot be rolled out until a new threshold alerting system goes live. The launch of that system has been delayed due to current systems issues. As a result, the timeline is now very tight. Confidence in forecast: Moderate | Delivered |
| KR 4.3: Deliver upgraded flood warning models in 2 highest priority areas. | Q4 | 0.29 | 0.29 | - | - |  | Continuing progress on upgrading flood models however full delivery is dependent on key staff resourcing. Confidence in forecast: Moderate | Delivered |

Overall objective score = 0.50

## Water Environment

Our ambition is for the water environment to be protected with no deterioration of condition and that more of our water environment is improved to a good or better condition.

### WE OKR5 Deliver river basin management plan programme of actions to improve the water environment

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR5.1: Review and update our monitoring strategy for the water environment. | Q3 | N/A | N/A | - | - |  | On track for completion. Confidence in forecast: High | Delivered |
| KR 5.2: Complete 2025 monitoring plan for water environment. | Q4 | 0.15 | 0.38 | - | - |  | Chemistry have delivered 71% and Ecology have delivered 81% of planned work. Where there are shortfalls, the priority is on classification and regulatory monitoring. Confidence in forecast: High | Delivered |
| KR 5.3: 90% of our programme of actions for the water environment are delivered. | Q4 | 0.40 | 0.54 | - | - |  | We continue to make progress but there is a risk around delivery of this key result. Due to the need for an agile response to project constraints and opportunities, and to maintain transparency and ambition, from Q2 we are focusing on tracking progress across key stages in the RBMP3 programme that cover scoping, in progress and complete. We are now tracking 144 key movements and remain committed to delivering 90% of these this financial year. At the end of Q2, we have delivered 70 key movements. Confidence: Low confidence in meeting our target is reflected in partial delivery being forecast. | Partial Delivery |
| KR 5.4: Three projects for the water environment are delivered by 31 March 2026 | Q4 | 0.50 | 0.50 | - | - |  | On track for completion. Work commenced at all three sites. Confidence in forecast: High | Delivered |

Overall objective score = 0.47

### WE OKR6 Prepare for future cycles of river basin management planning.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 6.1: Publish significant water management issues (SWMI) report by 22 Dec 2025. | Q3 | N/A | N/A | - | - |  | On track. We are aiming to publish the report in November 2025. Confidence in forecast: High | Delivered |
| KR 6.2: 100% completion of review of monitoring network for classification to understand the pressures and impacts, to prepare for the 2026 monitoring plan | Q3 | N/A | N/A | - | - |  | On track. Confidence in forecast: High | Delivered |
| KR 6.3: Target engagement with 100% of identified key stakeholders for significant water management issues consultation by 31 March 2026 | Q4 | N/A | N/A | - | - |  | On track. Key result is dependent on delivery and outputs of KR6.1. Confidence in forecast: High | Delivered |

Overall objective score = N/A. Delivery of all key results from Q3 onwards.

## Resource Efficiency

Our ambition is to fully play our part in helping Scotland to transition to a circular economy, and that the management of waste does not cause harm to the environment or communities.

### RE OKR7: Prepare to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR7.1: Launch baseline survey of Scotland’s businesses to assess awareness of the UK digital waste tracking service. | Q2 | N/A | 1 | - | - |  | Key result complete in Q2. Survey issued, completed & closed. Responses have been collated, and an analysis report is to be produced. | Delivered |
| KR7.2: 50% of SEPA’s requirements are incorporated into the UK digital waste tracking service by the DEFRA digital build team and is ready for testing by SEPA users. | Q4 | 0 | 0 | - | - |  | We continue to pursue clarity from DEFRA on digital build and what will be delivered by the end of Q4. Until confirmed we are forecasting partial delivery. Confidence: Objective is not entirely within SEPA's control Low confidence in meeting our target is reflected in partial delivery being forecast. | Partial delivery |
| KR7.3: SEPA is ready to support the introduction of the UK Digital Service by DEFRA for Scotland’s users in 2026. | Q4 | N/A | N/A | - | - |  | Key result will be progressed later in the year. Confidence: Objective is not entirely within SEPA's control Low confidence in meeting our target is reflected in partial delivery being forecast. | Partial delivery |

Overall objective score = 0.5

## Business Environmental Performance

Our ambition is to protect the environment and communities from harm; for Scotland to be an inhospitable place for environmental crime, and that regulation enables businesses to reduce their environmental impact.

### BEP OKR8: Ensure key stakeholders are engaged and informed on the necessary preparations required for compliance with the Biodegradable Municipal Waste (BMW) Landfill ban.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 8.1: 100% of landfill operators engaged through seminar and one to one engagement by 30 June 2025, to help prepare for compliance with BMW Landfill ban | Q1 | 1 | 1 | - | - |  | Delivered in Q1. | Delivered |
| KR 8.2: 75% of landfill operators surveyed are satisfied with SEPA guidance and support by August 2025 | Q2 | 0 | 0 | - | - |  | Proactive engagement has continued; however, formal satisfaction surveys have yet to be undertaken as the primary focus of the engagement work has been to facilitate the necessary discussions between Scottish Government and industry. We anticipate delivery by end of Q3. Confidence in forecast: High | Delivered |
| KR 8.3: Engage 100% of identified active waste management sites to raise awareness and help them prepare for compliance with Biodegradable Municipal Waste (BMW) Landfill ban by 30 Sep 2025 | Q2 | 0 | 0 | - | - |  | We remain on track with our preparations. Delivery is being impacted by factors out with SEPA’s control. The wider industry is engaged directly with Scottish Government regarding readiness and the Energy from Waste (EfW) capacity gap. Clarity on any potential amendments to the Biodegradable Municipal Waste (BMW) ban to address this capacity gap is expected from Scottish Government by end of October. We anticipate delivery by end of Q3. Confidence in forecast: High | Delivered |
| KR 8.4: 75% of active waste management sites surveyed are satisfied with SEPA guidance and support by Aug 2025 | Q3 | N/A | N/A | - | - |  | Key result will be progressed later in the year once clarity on the terms of the ban is understood. Anticipate delivery now by end of Q4 as this survey can only take place once KR8.3 is complete. Confidence in forecast: High | Delivered |
| KR 8.5: 100% of surveyed SEPA waste regulation colleagues are aware of the ban and compliance requirements by Dec 2025 | Q3 | N/A | N/A | - | - |  | Key result will be progressed later in the year once clarity on the terms of the ban is understood. A communications plan is being prepared to communicate this to SEPA colleagues ahead of 31 December 2025. Confidence in forecast: High | Delivered |

Overall objective score = 0.33

### BEP OKR9: Tackle environmental crime using interventions approach.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 9.1: Complete an interventions framework to enhance our current SEPA toolkit and improve partnership working. | Q2 | N/A | 1 | - | - |  | Key result complete in Q2. | Delivered |
| KR 9.2: Reduce the overall environmental risk score of identified illegal activities by 10%, from 2024-25 baseline (33.0 to 29.7), through targeted interventions | Q4 | 0.06 | 1 | - | - |  | Key result delivered. The target percentage reduction has been fully achieved but as activity can increase in risk as well as decrease, we cannot yet state that the key result has been completed. From Q3, we will extend the target to reduce the overall environmental risk score of identified illegal activities by 20% from 2024-25 baseline, by the end of Q4. | Delivered |
| KR 9.3: Lower the overall environmental risk score of high-risk sites by 10%, from 2024-25 baseline (88.6 to 79.7) | Q4 | 0.20 | 1 | - | - |  | Key result delivered. The target percentage reduction has been fully achieved but as activity can increase in risk as well as decrease, we cannot yet state that the key result has been completed. From Q3, we will extend the target to reduce the overall environmental risk score of identified illegal activities by 20% from 2024-25 baseline, by the end of Q4. | Delivered |
| KR 9.4: Implement and establish the interventions framework to increase our success in disrupting high risk environmental crime. | Q4 | N/A | N/A | - | - |  | On track. The implementation of the framework for the use of interventions continues to require further discussion. Enforcement Hub communications are being developed. Interventions will be included in the CLUE training on investigations due to commence mid-November. Training and roll out to conclude in March 2026. Confidence in forecast: Moderate | Delivered |

Overall objective score = 1

## Our Organisation

We are committed to public service reform, ensuring that we are a well-run organisation which achieves best value for the resources invested in us. We support our highly talented people to do great work for Scotland’s environment, creating a positive place to work.

### OO OKR10: Introduce effective digital public contact services for customers

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 10.1: Launch new digital contact methods for the public and our customers to contact SEPA | Q2 | N/A | 0 | - | - |  | This will be informed by the externally commissioned customer research, which is expected to outline findings by the end of this financial year. This is reflected in the forecast as not delivered. | Not Delivered |
| KR 10.2: Customer service standards implemented | Q2 | N/A | 0 | - | - |  | Work progressing through ongoing internal and external research to inform the development of our agency wide customer service standards. While this measure is linked to key result 10.1- launch of new digital public contact methods, it forms part of our wider customer experience strategy and how we design, assess and manage customer experience across the Agency. The strategy will include a roadmap with the delivery of data and digital to support public contact that meets user needs and accessibility. Our customer service standards are expected to be developed through a test and learn approach and implemented by the end of Q4, to inform our understanding. There is a tender to continue with current platform provider as we undergo transformation and scoping requirements for our longer-term platform that will include digital contact functionality. Confidence in forecast: High | Delivered |
| KR 10.3: Target of customer digital interactions are resolved within service level agreement timeframes | Q4 | N/A | 0 | - | - |  | This key result is dependent on the delivery of KR10.1 - Launch New Digital Contact Methods, which has been paused, and Key Result 10.2, now scheduled for completion in Q4. As a result, this will not be delivered in 2025/26. This is reflected in the forecast as not delivered. | Not Delivered |

Overall objective score = 0

### OO OKR11: Deliver our People Strategy to build a safe, welcoming and high performing environment which empowers our people to be purposeful, professional and passionate

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 11.1: Launch strategic approach to wellbeing and improved offer of mental health and wellbeing support to colleagues. | Q1 | 1 | 1 | - | - |  | Key Result completed Q1 | Delivered |
| KR 11.2: 75% of recruiting managers reporting improved satisfaction with applicant tracking system. | Q3 | 0 | 0 | - | - |  | Launched new Applicant Tracking System (ATS) - Talos360 in Q2. Key result will be progressed in Q3. Confidence in forecast: High | Delivered |
| KR 11.3: Launch of colleague engagement plan. | Q3 | N/A | N/A | - | - |  | Work is progressing to produce an employee engagement plan for the People Strategy. We are working collaboratively on identifying areas for pulse surveys and an all employee survey design. We have also completed engagement in specific activities launched as part of the People Strategy including Management Means. Confidence in forecast: High | Delivered |
| KR 11.4: 50% of colleagues accessing leadership or personal development opportunities through e-learning, workshops and facilitated programmes. | Q4 | 0.74 | 1 | - | - |  | Key result complete in Q2. We have exceeded our target for 2025/26, with 54.8% of colleagues accessing leadership or personal development opportunities through e-learning, workshops and facilitated programmes. | Delivered |

Overall objective score = 0.66

These are national outcomes for Scotland and SEPA plays a contributing role.

These are national outcomes for Scotland and SEPA plays a contributing role.

These are national outcomes for Scotland and SEPA plays a contributing role.

Please note, the Q1 report incorrectly showed a score of 0.5 for KR11.4. This should have been 0.74.