February 2026

Quarter 3 2025-2026

Corporate Performance Summary Report

# Contents

Contents	1

1. Executive Summary	2

Key highlights	2

Exceptions and recovery	4

2. Performance Summary	7

2.1 Annual Objectives and Key Results (OKRs) – Progress and exception summary	8

2.2 Key strategic and operational performance indicators – Progress and exception summary	12

3.	Performance Updates	20

Net Zero	20

Climate Resilience	27

Water Environment	34

Resource Efficiency	40

Business Environmental Performance	43

Our Organisation	51

If you would like this document in an accessible format, such as large print, audio recording or braille, please contact SEPA by emailing: equalities@sepa.org.uk

# 1. 	Executive Summary

This year’s Annual Operating Plan includes a suite of performance measures aligned to our corporate plan priorities. These aim to measure how we are fulfilling our long-term mission of protecting Scotland’s environment and communities, as well as how we are performing as an organisation overall. Our measures include:

- Annual objectives and key results (OKRs) which set out our clear, short-term areas of focus for us to target ambitious, measurable change and impact.

- Strategic and operational key performance indicators (KPIs) which provide a continuous view of our performance.

Each quarter we produce a report to explain how we are progressing with our measures.  This is the quarter three report covering the period 1 October 2025 to 31 December 2025.

## Key highlights

Net zero

- We completed direct engagement with the three pilot sites, as we look to develop our regulatory role with a more integrated approach to energy efficiency and industrial decarbonisation. Two from our list of energy intensive sites and one as an Outcome Based Collaborative Regulation (OBCR) site.

- We successfully achieved our Silver Carbon Literate Organisation status. Carbon Literacy training for SEPA staff is a cornerstone of our work to help Scotland achieve net zero and to reduce our own emissions. We continue to roll out the training across the organisation.

Climate resilience

- We completed the risk assessment database build and used the statistical output to inform the revised National Flood Risk Assessment (NFRA) for Scotland which was published in December.

- 100% of water scarcity warnings and alerts were issued on time in Q3.

Water Environment

- As part of the River Basin Management Plan programme of actions, we have completed three Water Environment Fund projects at Back Burn, the River Nith and Halter Burn. This key result (KR 5.4) has been delivered early, ahead of the original Q4 target. We have also successfully reviewed and updated the monitoring strategy for the water environment.

- We published the Significant Water Management Issues (SWMI) report on time in Q3.

- 100% of the monitoring network has been reviewed in preparation for River Basin Management Plan 4 (RBMP4).

- The 2025/2026 bathing water classifications were published on time in November 2025. We met our target with 96.6% of bathing waters classified as excellent, good or sufficient.

Business Environmental Performance

- On 1 November 2025, the Integrated Authorisation Framework was extended to include the regulation of waste, water and industrial activities, delivering a key milestone due in Q3. This was supported by a significant internal training and communications programme to ensure staff and regulated businesses were prepared for the change.

- In addition, we met the deadline to launch a new Digital Application System, enabling applicants to apply digitally and permitting staff to manage applications from receipt through to determination. Together, this programme of work significantly reduces regulatory complexity for business while supporting our organisational transformation to become more efficient and effective.

- We achieved our extended target to reduce the overall environmental risk score of high risk sites earlier than planned - by Q3 instead of Q4.

- By the end of Q3, we have carried out 170 successful interventions, exceeding the 167 delivered during the entire 2024/25 period. Consequently, KPI BEP01 has been achieved ahead of year end.

- The Radioactivity in Food and the Environment Report (RIFE 30) was published in October, a milestone due in Q3.

Our organisation and transformation

- We successfully launched our colleague engagement plan, delivering 94% of planned engagement sessions for the 2025/26 year to date.

- 78.5% of recruiting managers reported improved satisfaction with the new applicant tracking system, exceeding our target of 75%.

- We have delivered against our objective OKR11 Deliver our People Strategy to build a safe, welcoming and high performing environment which empowers our people to be purposeful, professional and passionate.

- We successfully launched our Data Strategy, delivering a milestone due in Q3. This defines the vision, business outcomes, strategic objectives and delivery roadmap, for creating and capturing value through data and analytics for SEPA and our customers over the next three years.

## Exceptions and recovery

Net zero

- The cumulative mileage of non-SEPA owned fleet vehicles for Q1 and Q2 2025/26 shows an 8.7% increase from same reporting period in 2024/25. We therefore continue to forecast that a reduction in mileage of non-SEPA owned vehicles by 10% will not be delivered in 2025/26. A cross-organisation action plan is being implemented to address this, which includes portfolio/team travel targets and fleet plans, using newly introduced telematics data to more effectively locate our fleet vehicles where needed, emphasising expected behaviours through our travel hierarchy and planning to review people policies later in 2026.

Climate Resilience

- We have made progress on our objective to ensure effective and resilient flood services that are designed to meet future requirements. However, there are risks to the delivery of key results 4.2 and 4.3. Progress against the target to increase the number of stations that deliver hydrometry data in near real time (within 30 minutes) from 70% to 95%, has been impacted by dependency delays, as well as additional testing and site constraints. Delivery of upgraded flood warning models in two highest priority areas has also been delayed, with one stage now not expected to be completed in Q4. Risk associated with key staff dependencies continue to be actively managed and partial delivery is currently forecast.

Resource Efficiency

- We are continuing to pursue key results in our preparations to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government. This is an externally led, four-nations project run by DEFRA, and our confidence in delivery of this objective is influenced by the outcomes not entirely being within SEPA's control. We are continuing to forecast partial delivery for key results 7.2 and 7.3 as the DEFRA led digital build project have noted delays and there is ongoing uncertainty around regulatory requirements. We continue to work closely with DEFRA as well as Scottish Government; however, it remains unclear to what extent SEPA’s requirements will be delivered by the end of the year.

Business Environmental Performance

- There is risk around achieving our KPI target of completing 80% of in scope planned permit reviews and variations for 2025/26. Progress with the permit reviews has been delayed by the transition to the Environmental Authorisations (Scotland) Regulations (EASR) and the requirement for clarification around some technical aspects of the indirect discharge and fish feed manufacturers policy positions, as well as delays in obtaining both internal and external data. These issues are largely resolved, although the review of four fish feed manufacturers permits will now take longer than originally anticipated. A plan will ensure the internal data is provided in a phased manner to coincide with the ongoing and planned permit reviews. We are working with operators to ensure their data is submitted in the shortest possible timescales.

Our Organisation

- The launch of our Digital Strategy (originally a milestone due in Q3), has been delayed until Q4 so that our new Head of Digital and Enterprise Architecture has sufficient time to review SEPA’s approach to digital.

- As reported fully in Q2, there has been progress on the development of SEPA’s first Customer Experience Strategy, supported by commissioned external customer research due later this year. To ensure future‑proofing, the delivery of key results 10.1 and 10.3 has been paused for review in 2026/27, with no associated risks. In the interim, the Customer Hub remains fully resourced and effective. Work continues on the platform tender process, and key result 10.2 (excluding new digital channels), will be progressed through a test‑and‑learn approach with implementation by the end of Q4, to align with the broader programme timeline.

We continue to develop our reporting mechanisms and style to enable effective scrutiny of our delivery in the upcoming period.

# 2. 	Performance Summary

This section provides a high-level, visual summary of the status of each OKR and KPI for quarter three.

Figure 1: Overall OKRs by status as at Q3. 				   		Figure 2: Breakdown of overall OKRs by status and quarter.

(N=11)

Figure 3: KPIs by status as at Q3.    				   			Figure 4: Breakdown of KPIs by status and quarter.

## 2.1 Annual Objectives and Key Results (OKRs) – Progress and exception summary

This section provides a summary of progress and any exception commentary for our OKRs as at Q2. Table 1 outlines the scoring matrix applied. We have also noted guidance to consider when reviewing the report.

Table 1: OKR scoring matrix

| Scoring | Status | Description |
| --- | --- | --- |
| 0.70 to 1.00 |  | Delivering – We are delivering or have delivered against our OKR measure this quarter. |
| 0.31 to 0.69 |  | Progressing – We are making measurable progress against delivery of our OKR measure this quarter but remain short of our target. |
| 0.00 to 0.30 |  | No progression – We did not make significant measurable progress towards delivery of our OKR measure this quarter. |
| Not applicable |  | Not started – Activity has not yet started or is not yet due for our OKR measure this quarter. |
| 1.00 |  | Complete – The OKR measure is complete and the deadline for completion has passed. |

Key results and Objectives Scoring Guidance

When reviewing the OKRs scoring in the report, please consider the guidance below:

Key results scores

- Key results are scored on a sliding scale between 0 and 1, with 1 representing 100% delivery.

- Key result scores are typically set to measure the desired outcomes, not actions or activity. The score therefore aims to show what has been delivered in the quarter in terms of quantifiable impact or change, not what activity may have been undertaken. As a result, a KR can be scored ‘0’ or N/A and still be on track for delivery by the due date.

- For example, let us assume we have a key result to ‘Replace 1000 monitoring stations by Q1’. If we replace 300 monitoring stations, the key result would be scored as 0.3. If we replace 950 monitoring stations, the key result would be scored as 0.95.

- As key results are designed to drive ambitious, stretch goals with measurable change and impact, any score over 0.70 is considered as delivering against the measure.

Overall objective score

- An overall objective score equates to the cumulative score of each key result, divided by the number of relevant key results.

- For example, assuming we have three KRs with scores provided, the calculation would be ‘KR1 score + KR2 score + KR3 score’ divided by three = Overall OKR score. If a key result is noted as not started, this is not included in the cumulative calculation.

Table 2: OKR progress and exception summary

| Code | Priority | Objectives | Q1 score | Q2 score | Q3 score | Q4 score | Status | Q3 Exception Commentary | Annual Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NZ OKR1 | Net Zero | Develop our regulatory role with a more integrated approach to energy efficiency and industrial decarbonisation. | 0 | 0.66 | 1 | - |  | We are delivering against this measure. Key Results 1.1 and 1.2 have been fully delivered. Key Result 1.3, the report outlining the results of our work with the pilot sites, is due to be delivered in Q4. | Delivered |
| NZ OKR2 | Net Zero | Transform our workspaces and fleet to minimise emissions, reduce costs and move to co-located workspaces by default and zero emissions fleet by 2030. | 0.33 | 0.25 | 0.5 | - |  | We are on track for delivering three out of the four Key Results for this objective, with significant progress made. A cross organisational action plan is being implemented for Key Result 2.3. | Partial Delivery |
| CR OKR3 | Climate Resilience | Improve awareness and understanding of flood and drought risk, including implications of climate change, to support effective decision making. | 0.80 | 0.90 | 1 | - |  | We are delivering against this measure. Key Results 3.1 and 3.2 have been delivered. Key Results 3.3 and 3.4 are due to be delivered in Q4. | Delivered |
| CR OKR4 | Climate Resilience | Ensure effective and resilient flood services which are designed to meet future requirements. | 0.50 | 0.50 | 0.57 | - |  | We are on track for delivering one of the three Key Results for this objective. | Partial Delivery |
| WE OKR5 | Water Environment | Deliver River Basin Management Plan programme of actions to improve the water environment. | 0.35 | 0.47 | 0.84 | - |  | Delivery on track. | Delivered |
| WE OKR6 | Water Environment | Prepare for future cycles of river basin management planning. | N/A | N/A | 1 | - |  | We are delivering against this measure. Key Results 6.1 and 6.2 have been delivered. Key Result 6.3 is due to be delivered in Q4. | Delivered |
| RE OKR7 | Resource Efficiency | Prepare to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government. | 0 | 0.50 | 0.50 | - |  | We are on track for delivering areas within our control. We continue to pursue clarity from DEFRA’s digital build team regarding SEPA’s requirements and what will be delivered by Q4. Until this is received, we are forecasting partial delivery. | Partial Delivery |
| BEP OKR8 | Business Environmental Performance | Ensure key stakeholders are engaged and informed on the necessary preparations required for compliance with the Biodegradable Municipal Waste (BMW) Landfill ban. | 0.33 | 0.33 | 0.20 | - |  | We remain on track with our preparations. During Q3 SEPA systems were put in place to support the temporary Regulatory Position Statement (tRPS) and enable operator compliance. As a result of the late policy change, the decision has been taken not to engage with stakeholders until Q4 to assess satisfaction and awareness with both preparatory guidance prior to the tRPS being published and the revised process and accompanying guidance and support following the publication of the tRPS. We anticipate delivery by end of Q4. | Delivered |
| BEP OKR9 | Business Environmental Performance | Tackle environmental crime using interventions approach. | 0.13 | 1 | 0.91 | - |  | Delivery on track. New stretch targets were implemented from Q3. Key Result 9.4 is not due to be delivered until Q4. | Delivered |
| OO OKR10 | Our Organisation | Introduce effective digital public contact services for customers. | N/A | 0 | 0 | - |  | We are awaiting results from externally commissioned customer research to inform our strategy development, which is expected by the end of this financial year. It is important we use the findings to inform the new digital contact methods (KR10.1) as well as the target service level agreement timeframes (KR10.3), to ensure these are future proof. As a result, we have decided to pause these for now and review them for 2026/27. We continue to progress Customer Service Standards implementation (KR10.2) (excluding the new digital channels) and now aim to have these in place by the end of Q4 to align with the broader programme timeline. | Partial Delivery |
| OO OKR11 | Our Organisation | Deliver our People Strategy to build a safe, welcoming and high performing environment which empowers our people to be purposeful, professional and passionate. | 0.58 | 0.66 | 1 | - |  | We have delivered against this objective. All key results have been delivered. | Delivered |

## 2.2 Key strategic and operational performance indicators – Progress and exception summary

A high-level summary of the progress of each key performance indicator aligned to our corporate plan priorities for quarter two is below.

Table 3: KPI progress and exception summary

| Code | Priority | Performance Indicator and Trajectory | Measure Type | Baseline | Target | Q3 Result | Q3 Status | Q3 Commentary | Annual Forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NZ01 | Net Zero | Annual greenhouse gas emissions in the Scottish Pollutant Release Inventory– Reducing | Strategic – Indirect influence | Baseline provided from 2007 Scottish Pollutant Release Inventory (SPRI) | Publish SPRI on time and in accordance with the Code of Practice – SEPA responsibility. Reduce annual greenhouse gas emissions – National outcome for Scotland, SEPA plays a contributing role. | 2024 SPRI data published on time on 30 September 2025. 3.85% reduction in greenhouse gas emissions. | Achieved | We published SPRI data on time and in accordance with the Code of Practice. Greenhouse gas emissions from all SEPA-regulated industrial facilities fell by 3.85% (0.37 megatonnes carbon dioxide equivalent) (CO2e), compared with 2023. This is continuing a long-term downward trend overall since 2007. The energy sector remained the highest emitting sector, with 38.6% of total industrial greenhouse gas emissions. However, energy sector emissions fell by 7.4% from 2023 to 2024 largely due to changes in production outputs. | Achieved |
| NZ02 | Net Zero | Annual reports of greenhouse gas emission by SEPA - Reducing | Strategic – Direct Control | 1742 tCO2e in 2022/23 | Reduce direct emissions by 15% by March 2026 - Target: 1481 tCO2e. | 873.15 tCO2e | Partially Achieving | Progress against this KPI is reported one quarter in arrears. Data is for Q1 and Q2 of 2025/26 (April to September 2025). Total emissions were 873.15 tCO2e. This is almost the same as our emissions in the equivalent period of our baseline year (2022/23). The result is almost entirely due to a significant increase (by 217%) in emissions from our marine survey vessel, the Sir John Murray (SJM), in the same period of our baseline year and masks positive performance in other areas. Emissions from workspaces are down by more than 20% and from travel (excluding SJM) by more than 8.5% in the same period of our baseline year 2022/23. | Partially Achieved |
| NZ03 | Net Zero | Percentage of vehicles in SEPA fleet that are zero emissions - Increasing | Operational – Direct control | 25 EVs in SEPA’s fleet as of 1 April 2025 | 26 EVs in SEPA fleet as a minimum by 31 March 2026 | 26 EVs | Achieved | We received delivery of an additional electric vehicle (EV) in July 2025, bringing the total number of EVs in the fleet to 26. | Achieved |
| NZ04 | Net Zero | Number of SEPA solely owned or leased buildings - Reducing | Operational – Direct Control | 11 buildings solely owned or leased by SEPA as of 1 April 2025 | Reduction of 2 workspaces per annum. | 1 | Partially Achieving | We completed the exit of our Glasgow workspace in October 2025. We are in the process of finalising the legal arrangements for our early exit from Strathallan House, Stirling. | Achieved |
| CR01 | Climate Resilience | Number of flood warnings and alerts issued by SEPA - Maintaining | Strategic – Direct control | Average number of alerts (244) and warnings (342) issued on an annual basis calculated over the last 14 financial years. | Maintain - The number of reports and warnings is dependent on the duration of a flood event and associated conditions. | 76 regional flood alerts 143 local flood warnings. | Achieving | Cumulative total for the year is 160 regional flood alerts and 171 local flood warnings. The period was marked by two periods of heavy rainfall and enhanced (Amber) flood risk - during Storm Amy at the start of October and around the period of 13-14 December. The main impacts were on the transport network. | Achieved |
| CR02 | Climate Resilience | Number of water scarcity warnings and alerts issued by SEPA - Maintaining | Strategic – Direct control | 23 x weekly water scarcity reports 1 x autumn water and 1 x winter water situation report. 914 normal conditions. 152 early warning. 12 alert. 1 moderate scarcity. Nil significant scarcity. | Maintain - The number of reports and alerts/ warnings is dependent on the duration of a water scarcity event and associated conditions. | 5 weekly reports issued with the following breakdown on water scarcity levels: 151 normal conditions. 37 early warning. 29 alert. 14 moderate scarcity. 17 significant scarcity. | Achieving | Cumulative total for the year is 29 weekly reports issued, with the following breakdown on water scarcity levels: 533 Normal, 365 Early Warning, 252 Alert, 193 Moderate and 67 Significant. | Achieved |
| CR03 | Climate Resilience | Percentage of daily Flood Guidance Statements and Scottish Flood Forecasts issued on time ​- Maintaining | Operational – Direct control | 2023/24 84% by 10:30 98% by 11:00 | At least 84% of Flood Guidance Statements are issued by 10:30am and 98% by 11:00am. The Scottish Flood Forecast is published at the same time. | 83.7% of the Flood Guidance Statements were issued by 10:30 98.9% of Flood Guidance Statements were issued by 11:00. | Partially Achieving | Cumulative progress at Q3 ahead of target: - 90.2% Flood Guidance Statements issued by 10:30 - 99.3% Flood Guidance Statements were issued by 11:00 | Achieved |
| CR04 | Climate Resilience | Percentage of water scarcity warnings and alerts issued on time - Maintaining | Operational – Direct control | No baseline, first year of reporting. 2025/26 will establish the baseline. | Water Scarcity reports published on Thursdays by 15:00. 100% of messages to abstractors as a result of changes to locations status in relation to Water Scarcity level sent by Friday 15:00. | 100% | Achieving | 100% performance maintained from Q1 and Q2. All identified authorisation holders whose activities are affected by water scarcity and who have supplied up to date contact information was supplied to SEPA, received the appropriate Water Scarcity level advice within 24 hours of the Water Scarcity Report being made public. All new and reviewed contact details are updated as required. 11,014 total communications sent from Q1 to Q3, with breakdown shown below. Reduction in messages in Q3 resulting from fewer changes to locations status as we enter the end of the year. - Q1 – 5960. - Q2 – 4900. - Q3 - 154. | Achieved |
| CR05 | Climate Resilience | Number of people accessing flood warning information on SEPA’s website ​- Maintaining | Operational – Direct control | 896,038 annual users accessing SEPA flood forecasting and warning services web pages. Baseline derived using data from 1 January 2024 – 31 December 2024 | Maintaining – The number of users will be dependent on the duration of a flood event and associated conditions. | 195,197 views | Partially Achieving | Cumulative total for year is 365,061 views of SEPA flood forecasting and warning services web pages. This is a relatively low number compared to last year's nearly 900,000 views (40.7%) and reflects the relatively limited flood warning activity this year compared to last year, so less incentive for people to view our information. | Achieved |
| CR06 | Climate Resilience | Percentage of new developments approved in accordance with SEPA's advice on flood risk – Maintaining | Strategic – Direct Influence | 98.4% 2024/25 baseline. 1478 consultations on 946 separate planning applications. | Maintain >95%, recognising that exceptions may occur. | 98.5% of 270 consultations | Achieving | Four developments were approved against SEPA's advice this quarter, following notification to Scottish Ministers. Cumulative Q1 Q2, and Q3 performance is 98.2%. | Achieved |
| CR07 | Climate Resilience | Percentage of responses to planning consultations within time​ - Increasing | Operational – Direct control | 70% 2023/24 baseline | Increase the percentage of consultations responded to within time to over 80%. | 96.2% | Achieving | We responded to 457 planning consultations on time with 18 responses beyond time. Cumulative performance to date is 90.8%. 1615 on time, 163 beyond time. | Achieved |
| CR08 | Climate Resilience | Number of people registered to Floodline to receive flood alerts and warnings – Increasing | Operational – Direct Influence | 41,992 registrations at the end of March 2025 | An increase from 41,992 registrations by the end of March 2026 | 42,175 registrations | Achieving | We had a net increase of 405 registrations to Floodline compared to Q2. 1,146 new registrations and 741 deregistrations. We have been promoting the Floodline service for “winter readiness” across SEPA channels including our newsletter, social media, media releases and internally. We have also sent an annual reminder message to existing customers to confirm that their details are up to date, which has led to some deregistrations (for example because people have moved out of an area). Owing to the volume of deregistrations, we anticipate overall numbers will remain at approximately 42,000 and cannot guarantee that registrations will surpass 41,988. Consequently, the measure is forecast as partially achieved. | Partially Achieved |
| WE01 | Water Environment | Classification of water bodies across Scotland - Increasing | Strategic – Direct Influence | 2020 data (start of third RBMP) Good or better overall condition = 66% | National outcome for Scotland and SEPA plays a contributing role As set out in RBMP3: Good or better overall condition = 81% by 2027 | Good or high overall condition = 67% | Achieving | Classification 2024 reports good or high overall condition as 67%. 2449 out of 3652 water bodies are at good or high overall condition. This is an improvement compared to the 2020 baseline of 66%. | Achieved |
| WE02 | Water Environment | Number of water bodies at High, Good, Moderate, Poor or Bad status/potential​ for water quality. – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP) Good or better overall condition = 87% | As set out in RBMP3: Good or better overall condition = 92% by 2027 | Good or high water quality = 87% | Partially Achieving | Classification 2024 reports good or high water quality at 87%. This is stable compared to the 2020 baseline of 87%. | Partially Achieving |
| WE03 | Water Environment | Number of water bodies at High, Good, Moderate, Poor or Bad status/potential​ for water flows and levels – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 90% | As set out in RBMP3: Good or better overall condition = 96% by 2027 | Good or high water flows and levels = 89% | Not Achieving | Classification 2024 reports good or high water flows and levels at 89%. The reported decrease from the 2020 baseline of 90% is due to changes in assessment and reporting methodologies. There has been no underlying environmental change; results reflect updated classification in line with new information. These changes will be further reviewed through River Basin Management Planning (RBMP) workstream. | Not Achieved |
| WE04 | Water Environment | Number of surface water bodies at High, Good, Moderate, Poor or Bad status/potential​ for physical condition. – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 90% | As set out in RBMP3: Good or better overall condition = 92% by 2027 | Good or high physical condition = 91% | Achieving | Classification 2024 reports good or high physical condition at 91%. This is an improvement compared to the 2020 baseline of 90%. | Achieved |
| WE05 | Water Environment | Number of surface water bodies at High, Good, Moderate, Poor or Bad status/potential​ for fish migration – Improvement | Strategic – Direct Influence | 2020 data (start of third RBMP). Good or better overall condition = 88% | As set out in RBMP3: Good or better overall condition = 99% by 2027 | Good or high status/potential​ for fish migration = 90% | Achieving | Classification 2024 reports good or high status /potential for fish migration at 90% This is an improvement compared to the 2020 baseline of 88%. | Achieved |
| WE06 | Water Environment | Percentage of bathing waters meeting excellent, good, or sufficient quality standards​– Improvement | Strategic – Direct Influence | 2024/2025 baseline classification 89 bathing waters with 96.6% sufficient or better | Achieving - the percentage of bathing waters at excellent, good and sufficient classifications to meet or exceed the baseline percentage. | Met baseline percentage of 96.6% | Achieving | The 2025/2026 bathing water classifications were published on target on 18 November 2025. The percentage of bathing waters at excellent, good and sufficient classifications have met the baseline percentage of 96.6%. | Achieved |
| RE01 | Resource Efficiency | Rates of waste to landfill in annual Scottish household waste data - Reducing | Strategic – Indirect influence | 2011 data (1.45 million tonnes of Scottish household waste landfilled) | Rates of waste to landfill to decrease – National outcome for Scotland and SEPA plays a contributing role. Publish Scottish household waste data on time and in accordance with the Code of Practice – SEPA responsibility. | Published 28th October 2025 – on time | Achieving | The 2024 Official Statistics report was published on time on 28 October 2025 along with press release. The total quantity of all waste landfilled in Scotland in 2024 was 1.81 million tonnes, a reduction of 8.6% from 2023. This continues a long-term trend with a reduction of 74.3% from 2005 and is the lowest annual amount of waste landfilled in Scotland in the time series. | Achieved |
| BEP01 | Business Environmental Performance | Number of successful interventions per year – Increasing | Strategic – Direct Influence | 2024/25 baseline: 167 interventions. | Increasing number of interventions | 170 successful interventions carried out up to the end of Q3. | Achieved | As at the end of Q3, we have carried out a total of 170 successful interventions, exceeding the 167 delivered during the entire 2024/25 period. | Achieved |
| BEP02 | Business Environmental Performance | Percentage of environmental monitoring statutory reports published by the scheduled date – Maintaining | Operational – Direct control | 2024/25 baseline – 100% Four out of four on-time publication rate from the previous year. | 100% - Four out of four reports published on-time | 100% - Four out of four reports published | Achieving | We published two reports: the Annual Bathing Water classification report and the Aquatic classification reports in November 2025. We have published all four reports on time. | Achieved |
| BEP03 | Business Environmental Performance | Percentage of statutory reviews completed – Increasing | Operational – Direct control | 2024/25 baseline 31% | 80% of in scope planned permit reviews and variations by year end (39 Best Available Techniques (BAT) conclusions / 13 medium combustion plant permit variations) | 20 permit variations issued by Q3 (38.5%) | Not Achieving | The Q3 target is 60% of statutory reviews complete which equates to 31 of the in-scope permits. 20 permit variations have been issued. Progress with the permit reviews has been delayed by the transition to EASR and the requirement for clarification around some technical aspects of the indirect discharge and fish feed manufacturers policy positions as well as delays in obtaining both internal and external data. These issues are largely resolved although the review of four fish feed manufacturers permits will now take longer than originally anticipated. A plan will ensure the internal data is provided in a phased manner to coincide with the ongoing and planned permit reviews. We are working with operators to ensure their data is submitted in the shortest possible timescales. | Not Achieved |
| BEP04 | Business Environmental Performance | Percentage of applications determined within statutory determination times – Increasing | Operational – Direct control | 2023/24 baseline: 92% all applications 75% for permitting licences / 87% for permitting registrations | Maintain the percentage of applications determined within statutory timelines. | 94% of all applications. 86% for permitting licences / 95% for permitting registrations | Achieving | We are maintaining high performance for applications determined within the statutory determination times. | Achieved |

# Performance Updates

## Net Zero

Our ambition is to fully play our part in helping Scotland become a net zero country by 2045 and reduce our own emissions towards net zero.

### NZ OKR01: Develop our regulatory role with a more integrated approach to energy efficiency and industrial decarbonisation.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR1.1: 100% of requested energy efficiency data received from energy intensive sites. | Q2 | 0 | 1 | 1 | - |  | Key result delivered in Q2. | Delivered |
| KR1.2: Direct engagement with three pilot sites, from the list of energy intensive sites. | Q3 | N/A | 0.33 | 1 | - |  | We have had direct engagement with the three pilot sites. Two from our list of energy intensive sites and one as an Outcome Based Collaborative Regulation (OBCR) site. This direct engagement will expand in the next quarter. Confidence in forecast: High | Delivered |
| KR1.3: Deliver options assessment of regulatory approaches in relation to energy efficiency and industrial decarbonisation. | Q4 | N/A | N/A | N/A | - |  | The report outlining the results of our work with the pilot sites will be developed in Quarter 4. We will report to the Regulation, Business and Environment Management Team at the end of Q4. Confidence in forecast: High | Delivered |

Overall objective score = 1

### NZ OKR02: Transform our workspaces and fleet to minimise emissions, reduce costs and move to co-located workspaces by default and zero emissions fleet by 2030.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 2.1: Launch strategic approach to our Fleet, working to reduce emissions in our owned vehicle fleet. | Q1 | 1 | 1 | 1 | - |  | Key result delivered in Q1. | Delivered |
| KR 2.2 100% of all business travel by fleet vehicles is tracked. | Q3 | 0 | 0 | 0 | - |  | Delivery has been delayed due to required Data Protection Impact Assessment (DPIA) work. The revised delivery timeframe is Q4, subject to completion of the DPIA and approval by the Change & Control Board (CaCB). Confidence in forecast: High/Moderate | Delivered |
| OKR 2.3: Reduce mileage of non-SEPA owned fleet vehicles by 10%. | Q4 | 0 | 0 | * | - |  | *Reporting for this Key Result is one quarter in arrears. Q2 data shows a slight decrease compared with Q2 2024/25. Cumulative Q1–Q2 performance for 2025/26 shows an 8.7% increase against the same period in 2024/25. A cross-organisation action plan is being implemented, with delivery dependent on several key factors, including portfolio restructures. Confidence in achieving the 10% annual reduction against the 2024/25 baseline is currently low, which is reflected in the annual forecast. | Not Delivered |
| KR 2.4: 5% reduction of greenhouse gas emissions from SEPA workspaces by realising savings through workspaces transformation. | Q4 | 1 | 1 | * | - |  | *Reporting for this Key Result is one quarter in arrears. Q2: 7.36% reduction against Q2 2024/25 figures. Progress on track. Glasgow sale and exit complete. Stirling exit should complete early 2026. Q1: 7.29% reduction against Q1 2024/25 figures. Cumulative Q1 and Q2: 7.32% reduction against Q1 and Q2 2024/25 figures. Workspace emissions are subject to multiple variables and as such we cannot yet state that the key result has been completed. Confidence in forecast: High | Delivered |

Overall objective score = 0.5

## Climate Resilience

Our ambition is that the damaging impacts of floods and droughts is reduced, and that operators are prepared for and resilient to the impacts of a changing climate.

### CR OKR3: Improve awareness and understanding of flood and drought risk, including implications of climate change, to support effective decision making.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 3.1: Complete risk assessment database build to produce statistical output for flood risk assessment service reporting. | Q2 | 0.80 | 0.90 | 1 | - |  | Key result delivered. Completed in November 2025 and the results used in OKR3.2 National Flood Risk Assessment publication. | Delivered |
| KR 3.2: Publish a revised National Flood Risk Assessment for Scotland by 31 December 2025. | Q3 | N/A | N/A | 1 | - |  | Key result delivered. National Flood Risk Assessment for Scotland published in December 2025 | Delivered |
| KR 3.3: Engage five national utility infrastructure owners to increase awareness of the potential wider impacts of flooding. | Q4 | N/A | N/A | N/A | - |  | Key result was dependent on delivery of KR3.2, so will be progressed during Q4, subject to availability of stakeholders. Confidence in forecast: Moderate to high | Delivered |
| KR 3.4: All irrigation licences varied to include a time limited water scarcity condition. | Q4 | N/A | N/A | N/A | - |  | On track for delivery in Q4. All licence holders contacted and data set up for variation documents. Confidence in forecast: High | Delivered |

Overall objective score = 1

### CR OKR4: Ensure effective and resilient flood services which are designed to meet future requirements.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR4.1: Review all 10 flood services to identify improvements and future design requirements | Q2 | 0.70 | 0.70 | 0.70 | - |  | We have made progress in refining flood service improvements and future design requirements. Dependency on access to digital design partners to progress future design requirements for key prioritised flooding business needs. Confidence in forecast: Moderate | Delivered |
| KR 4.2: Increase the number of stations that deliver hydrometry data in near real time (within 30 minutes) from 70% to 95%. | Q4 | N/A | N/A | N/A | - |  | Work due to commence in Q4 onwards. Key dependencies on critical‑path delayed. Additional testing from system alarms, and asbestos‑related site constraints are impacting expected delivery. Forecast outcome is an increase from 70% to 85–90%. An increase to 95% remains possible but critical path now very tight. Forecasting partial delivery. | Partial Delivery |
| KR 4.3: Deliver upgraded flood warning models in 2 highest priority areas. | Q4 | 0.29 | 0.29 | 0.43 | - |  | One new stage complete during Q3 for Firth of Forth and Tay projects. However, the last stage is not expected to be completed in Q4. There are delays for the Borders scheme with completion expected but stretching in Q4. Risk around key staff dependency being actively managed. Forecasting partial delivery. | Partial Delivery |

Overall objective score = 0.57

## Water Environment

Our ambition is for the water environment to be protected with no deterioration of condition and that more of our water environment is improved to a good or better condition.

### WE OKR5 Deliver river basin management plan programme of actions to improve the water environment

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR5.1: Review and update our monitoring strategy for the water environment. | Q3 | N/A | N/A | 1 | - |  | Key result delivered. Overall evidence strategy and vision delivered. | Delivered |
| KR 5.2: Complete 2025 monitoring plan for water environment. | Q4 | 0.15 | 0.38 | 0.62 | - |  | Chemistry have delivered 79% and Ecology have delivered 86% of planned work, giving a combined delivery of 82.5% of Q3 targets. Where there are shortfalls, the priority is on classification and regulatory monitoring. We are confident in delivery of the majority of the plan overall (>80%), with some shortfalls in isolated areas. Confidence in forecast: High | Delivered |
| KR 5.3: 90% of our programme of actions for the water environment are delivered. | Q4 | 0.40 | 0.54 | 0.75 | - |  | Delivery against this key result is now on track, with progress across the scoping, in progress and complete stages. By the end of Q3, 98 of the 144 key actions have been completed. Progress has been strongest in the scoping stage, where delivery has exceeded expectations, with 27 additional actions completed beyond the original key result scope. These additional actions are not included in the performance calculations for this key result. Delivery against actions in the ‘In Progress’ stage is below target and is unlikely to be fully achieved within this financial year. Mitigations discussed with the Corporate Leadership Team including additional resource and improvements to business processes are expected to improve delivery in the next financial year. Confidence in forecast: High | Delivered |
| KR 5.4: Three projects for the water environment are delivered by 31 March 2026 | Q4 | 0.50 | 0.50 | 1 | - |  | Key result delivered. Three restoration projects complete. - Back Burn (river restoration) - River Nith - Former Polquhirter Treatment Works (river restoration) - Halter Burn (weir removal) | Delivered |

Overall objective score = 0.84

### WE OKR6 Prepare for future cycles of river basin management planning.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 6.1: Publish significant water management issues (SWMI) report by 22 Dec 2025. | Q3 | N/A | N/A | 1 | - |  | Key result delivered. SWMI report published on time. | Delivered |
| KR 6.2: 100% completion of review of monitoring network for classification to understand the pressures and impacts, to prepare for the 2026 monitoring plan. | Q3 | N/A | N/A | 1 | - |  | Key result delivered. Monitoring network fully reviewed to prepare for the 2026 monitoring plan. | Delivered |
| KR 6.3: Target engagement with 100% of identified key stakeholders for significant water management issues consultation by 31 March 2026 | Q4 | N/A | N/A | N/A | - |  | On track. Following the publication of SWMI report (Key Result 6.1) in Q3, we aim to engage with 100% of key stakeholders for a significant water management issues consultation by 31 March 2026. Confidence in forecast: High | Delivered |

Overall objective score = 1

## Resource Efficiency

Our ambition is to fully play our part in helping Scotland to transition to a circular economy, and that the management of waste does not cause harm to the environment or communities.

### RE OKR7: Prepare to support the 2026-2027 phase of the UK digital waste tracking service implementation by DEFRA and Scottish Government.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR7.1: Launch baseline survey of Scotland’s businesses to assess awareness of the UK digital waste tracking service. | Q2 | N/A | 1 | 1 | - |  | Key result complete in Q2. | Delivered |
| KR7.2: 50% of SEPA’s requirements are incorporated into the UK digital waste tracking service by the DEFRA digital build team and is ready for testing by SEPA users. | Q4 | 0 | 0 | 0 | - |  | Progress is being impacted by delays to the DEFRA led digital build. We continue to work closely with DEFRA; however, it remains unclear to what extent SEPA’s requirements will be delivered by the end of Q4. Confidence: This objective is not entirely within SEPA's control. Low confidence in delivering this key result is reflected in partial delivery being forecast. | Partial delivery |
| KR7.3: SEPA is ready to support the introduction of the UK Digital Service by DEFRA for Scotland’s users in 2026. | Q4 | N/A | N/A | N/A | - |  | Work progressing on the plan to support the introduction of the UK Digital Service focussed on waste receiving sites. Confidence: The required extent of our readiness depends on the DEFRA digital build in 2025/26, what parts of the service (if not the full the service) are ready for use, and what Scottish Government’s regulations will require of users and SEPA in 2026/27. We are therefore forecasting partial delivery. | Partial delivery |

Overall objective score = 0.5

## Business Environmental Performance

Our ambition is to protect the environment and communities from harm; for Scotland to be an inhospitable place for environmental crime, and that regulation enables businesses to reduce their environmental impact.

### BEP OKR8: Ensure key stakeholders are engaged and informed on the necessary preparations required for compliance with the Biodegradable Municipal Waste (BMW) Landfill ban.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q3 Status | Q3 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 8.1: 100% of landfill operators engaged through seminar and one to one engagement by 30 June 2025, to help prepare for compliance with BMW Landfill ban | Q1 | 1 | 1 | 1 | - |  | Key result delivered in Q1. | Delivered |
| KR 8.2: 75% of landfill operators surveyed are satisfied with SEPA guidance and support by August 2025 | Q2 | 0 | 0 | 0 | - |  | Proactive engagement has continued; however, formal surveys have yet to be undertaken. During Q3, SEPA systems were put in place to support the temporary Regulatory Position Statement (tRPS) and enable operator compliance. As a result, of the late policy change the decision has been taken not to engage with operators / active waste management sites until Q4 to assess satisfaction and awareness with both preparatory guidance prior to the tRPS being published and the revised process and accompanying guidance and support following the publication of the tRPS. We anticipate delivery by end of Q4. Confidence in forecast: High | Delivered |
| KR 8.3: Engage 100% of identified active waste management sites to raise awareness and help them prepare for compliance with Biodegradable Municipal Waste (BMW) Landfill ban by 30 Sep 2025 | Q2 | 0 | 0 | 0 | - |  | Please refer to the update for KR 8.2 above. Confidence in forecast: High | Delivered |
| KR 8.4: 75% of active waste management sites surveyed are satisfied with SEPA guidance and support by Aug 2025 | Q3 | N/A | N/A | 0 | - |  | Please refer to the update for KR 8.2 above. Confidence in forecast: High | Delivered |
| KR 8.5: 100% of surveyed SEPA waste regulation colleagues are aware of the ban and compliance requirements by Dec 2025 | Q3 | N/A | N/A | 0 | - |  | Please refer to the update for KR 8.2 above. Confidence in forecast: High | Delivered |

Overall objective score = 0.2

### BEP OKR9: Tackle environmental crime using interventions approach.

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 9.1: Complete an interventions framework to enhance our current SEPA toolkit and improve partnership working. | Q2 | N/A | 1 | 1 | - |  | Key result complete in Q2. | Delivered |
| KR 9.2: Reduce the overall environmental risk score of identified illegal activities by 10%, from 2024-25 baseline (33.0 to 29.7), through targeted interventions. Target increased to 20% from Q3. | Q4 | 0.06 | 1 | 0.74 | - |  | The original target of a 10% reduction has been fully delivered. From Q3 we extended the target to reduce the overall environmental risk score of identified illegal activities by 20%. We are currently on track and delivering against this key result. Confidence in forecast: High | Delivered |
| KR 9.3: Lower the overall environmental risk score of high-risk sites by 10%, from 2024-25 baseline (88.6 to 79.7). Target increased to 20% from Q3. | Q4 | 0.20 | 1 | 1 | - |  | Key result delivered. From Q3 we extended the target to reduce the overall environmental risk score of high risk sites by 20%. We are currently exceeding our target with a 22% reduction, but as activity can increase in risk as well as decrease, we cannot yet state that the key result has been completed. Confidence in forecast: High | Delivered |
| KR 9.4: Implement and establish the interventions framework to increase our success in disrupting high risk environmental crime. | Q4 | N/A | N/A | N/A | - |  | On track. Key procedures in place. Staff familiarisation is to commence in Q4; however, recruitment delays mean some staff training and rollout may not be completed by March 2026. As a result, confidence in fully delivering this key result is moderate. Confidence in forecast: Moderate | Delivered |

Overall objective score = 0.91

## Our Organisation

We are committed to public service reform, ensuring that we are a well-run organisation which achieves best value for the resources invested in us. We support our highly talented people to do great work for Scotland’s environment, creating a positive place to work.

### OO OKR10: Introduce effective digital public contact services for customers

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 10.1: Launch new digital contact methods for the public and our customers to contact SEPA | Q2 | N/A | 0 | 0 | - |  | This will be informed by the externally commissioned customer research, which is expected to outline findings by the end of this financial year. This is reflected in the forecast as not delivered. | Not Delivered |
| KR 10.2: Customer service standards implemented | Q2 | N/A | 0 | 0 | - |  | Work progressing through ongoing internal and external research to inform the development of our agency wide customer service standards. While this measure is linked to key result 10.1- launch of new digital public contact methods, it forms part of our wider customer experience strategy and how we design, assess and manage customer experience across the Agency. The strategy will include a roadmap with the delivery of data and digital to support public contact that meets user needs and accessibility. Our customer service standards are expected to be developed through a test and learn approach and implemented by the end of Q4, to inform our understanding. There is a tender to continue with current platform provider as we undergo transformation and scoping requirements for our longer-term platform that will include digital contact functionality. Confidence in forecast: High | Delivered |
| KR 10.3: Target of customer digital interactions are resolved within service level agreement timeframes | Q4 | N/A | 0 | 0 | - |  | This key result is dependent on the delivery of KR10.1 - Launch New Digital Contact Methods, which has been paused, and Key Result 10.2, now scheduled for completion in Q4. As a result, this will not be delivered in 2025/26. This is reflected in the forecast as not delivered. | Not Delivered |

Overall objective score = 0

### OO OKR11: Deliver our People Strategy to build a safe, welcoming and high performing environment which empowers our people to be purposeful, professional and passionate

| Key Results | Due date | Q1 score | Q2 score | Q3 score | Q4 score | Q2 Status | Q2 commentary | Annual forecast |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| KR 11.1: Launch strategic approach to wellbeing and improved offer of mental health and wellbeing support to colleagues. | Q1 | 1 | 1 | 1 | - |  | Key Result completed Q1 | Delivered |
| KR 11.2: 75% of recruiting managers reporting improved satisfaction with applicant tracking system. | Q3 | 0 | 0 | 1 | - |  | Key result delivered. Currently tracking at 78.5% survey respondents reported improved satisfaction with the new applicant tracking system. This will continue to be monitored, and any feedback received actioned where possible. | Delivered |
| KR 11.3: Launch of colleague engagement plan. | Q3 | N/A | N/A | 1 | - |  | Key result delivered. By the end of Q3, we have held 33 engagement sessions out of a total of 35 planned for the 2025/26 year to date (94%). Our target for this key result was to have launched the colleague engagement plan and implemented 90% by Q3. The plan has been deliberately iterative, evolving throughout the year to respond to colleague feedback and build sustained engagement rather than following a fixed, one‑off rollout. This adaptive approach has enabled strong momentum going into Q4 and supports continued delivery across the remainder of the year. | Delivered |
| KR 11.4: 50% of colleagues accessing leadership or personal development opportunities through e-learning, workshops and facilitated programmes. | Q4 | 0.74 | 1 | 1 | - |  | Key result complete in Q2. | Delivered |

Overall objective score = 1

These are national outcomes for Scotland and SEPA plays a contributing role.

These are national outcomes for Scotland and SEPA plays a contributing role.

These are national outcomes for Scotland and SEPA plays a contributing role.