# Agency Board meeting

## 29 September 2026

## Draft quarter 1 financial monitoring report for period ending 30 June 2026

Purpose:

This report is to provide an update to the Board on the following areas:

- Overall financial position

This is the first quarter financial report for 2026/27. Actual financial results for quarter 1 (1 April 2026 to 30 June 2026) show SEPA forecasting a balanced budget at the year-end.

- Capital budget

The capital summary for the period ending 30 June 2026 is provided in section 4 of this report.

### Recommendations:

The Board is asked to note SEPA’s financial performance for the period ending 30 June 2026.

Authors: Ian Bryce, Deputy Head of Finance; Rosaleen Burke, Head of Finance.

Corporate Leadership Team Sponsor: Angela Milloy, Chief Finance Officer.

Date: 31 August 2026

#### Table 1: Year to date (YTD) actuals and full year forecast

| Income and expenditure account at 30 June 2026 | Year to date actual £'000 | Year to date budget £'000 | Year to date variance £'000 | Forecast outturn £'000 | Annual budget £'000 | Forecast variance £'000 |
| --- | --- | --- | --- | --- | --- | --- |
| Grant in Aid | 25,000 | 25,000 | 0 | 58,053 | 58,053 | 0 |
| Charging Schemes | 51,078 | 51,578 | (500) | 59,381 | 59,647 | (266) |
| Other income | 270 | 289 | (19) | 1,387 | 1,385 | 2 |
| Total income | 76,348 | 76,867 | (519) | 118,821 | 119,085 | (264) |
| Staff costs | 19,300 | 19,622 | 362 | 79,188 | 79,819 | 631 |
| Other staff costs | 227 | 81 | (146) | 803 | 543 | (260) |
| Transport costs | 181 | 244 | 63 | 1,106 | 1,101 | (5) |
| Supplies & services | 4,719 | 4,909 | 190 | 25,444 | 25,315 | (129) |
| Property costs | 1,634 | 1,772 | 138 | 4,880 | 4,907 | 27 |
| Depreciation/impairment | 1,850 | 1,850 | 0 | 7,400 | 7,400 | 0 |
| Total operating costs | 27,911 | 28,518 | 607 | 118,821 | 119,085 | 264 |
| Operating surplus/ (deficit) | 48,437 | 48,349 | 88 | 0 | 0 | 0 |

### Introduction

  - At 30 June 2026, the year-to-date position shows a net underspend of £88k. A £607k underspend against the operating costs budget is partly offset by income being £519k below budget.

  - The full-year forecast is a balanced budget with a forecast reduction in income of £264k offset by a reduction in operating costs.

### Total income - £118.8m

  - Total income for the full year is forecast at £118.8m, which is £0.3m below the full year budget. This reflects a forecast that charging scheme income will be lower than budget.

#### Charging Scheme income - £59.4m

  - The full year charging scheme income forecast in June is £59.4m, which is £0.3m lower than budget mainly due to reduced annual charge income.

  - The reduction in annual charge income is mainly due to in-year changes in authorisation conditions, surrenders and revocations, and is partially offset by new authorisations.

#### Graph 1: Charging Scheme income by media

Graph 1 acronyms: RSA – Radioactive Substances Activity; COMAH – Control of Major Accident and Hazards

#### Other income - £1.4m

  - The other income is forecast to be £1.4m, which is in line with budget.

#### Revenue Grant in Aid (GiA) - £58.1m

#### Table 2: Grant in Aid

|  | Resource budget cash £’000s | Resource budget non- cash £’000s | Total £’000s |
| --- | --- | --- | --- |
| Base budget allocation 2026/27 | 44,230 | 7,400 | 51,630 |
| Budget adjustments |  |  |  |
| Sea lice monitoring | 82 |  | 82 |
| Emissions trading and F Gas | 396 |  | 396 |
| Contaminated land (assume staff secondment) | 40 |  | 40 |
| Water Environment Fund | 5,830 |  | 5,830 |
| Review of compliance | 75 |  | 75 |
| Total adjustments | 6,423 | 0 | 6,423 |
| Total revenue budget | 50,653 | 7,400 | 58,053 |

  - Revenue Grant in Aid (GiA) for 2026/27 has increased by £6.4m since the budget was set following additional funds for Water Environment Fund (WEF), emissions trading, compliance and contaminated land. The additional income will be fully offset by additional expenditure.

### Total revenue expenditure - £118.8m

  - Full year operating costs are forecast to be £0.3m below budget. Graph 2 provides a detailed breakdown by expenditure type.

#### Graph 2: Expenditure by type

### Staff costs

  - Budgeted staff costs represent 67% of total expenditure. Full year staff costs are forecast to be £0.6m below budget, mainly due to a higher level of vacancies than budgeted.

### Other staff costs

  - Other staff costs are forecast to be £0.3m above budget, mainly due to forecast expenditure on temporary workers and recruitment costs being higher than budgeted. These costs are generally funded from vacancy savings.

### Transport costs

  - Transport costs are in line with budget. A forecast overspend in mileage is offset by forecast underspends in vehicle repairs and hire costs.

### Supplies and services

  - Supplies and services are forecast to be £0.1m above budget. This reflects offsetting variances, including a £0.2m underspend on software purchases and maintenance, and £0.3m of overspends across licences, sub-contracted work and hardware.

  - Property costs are forecast to be £0.03m below budget. Overspends of £0.05m on property maintenance and rent are offset by underspends of £0.08m in dilapidations and professional fees.

### Capital expenditure summary

  - SEPA’s capital budget provided by Scottish Government (SG) for the year is £6.1m.

  - The base budget included planned overcommitment, recognising that capital projects may experience delays, expenditure slippage or changes to original budget estimates during procurement. Forecast expenditure is £0.4m above budget. This will be managed to achieve a balanced position at year-end.

#### Table 3: Capital budget 2026/27

| Function | Main projects within function budgets | Budget 2026/27 £'000 | June Forecast £'000 | Committed spend date £'000 | Forecast v budget spend £'000 |
| --- | --- | --- | --- | --- | --- |
| Governance | Integrated Digital Platform & Data as an Asset | 2,923 | 2,120 | 46 | (803) |
| Field Science & Operations | Gauging stations & LIDAR | 510 | 515 | 193 | 5 |
| Environmental Evidence | Filtration Systems carried forward from 2025/26 | 0 | 17 | 17 | 17 |
| Environmental Quality | Riverbasin Management Planning Information Systems | 85 | 85 | 0 | 0 |
| Environmental Forecasting & Warning | Coastal Asset Register & Flood forecasting. | 865 | 1,180 | 714 | 315 |
| Environmental Resilience & Enhancement | Reservoir Mapping | 130 | 30 | 0 | (100) |
| Digital | Server Hardware Refresh | 75 | 75 | 0 | 0 |
| Digital | Integrated Authorisation Framework Implementation | 1,267 | 1,117 | 760 | (150) |
| Workspaces | Office fit outs & fleet replacement | 1,378 | 1,394 | 297 | 16 |
| Savings required |  | (1,130) | (430) | 0 | 700 |
| Total baseline spend |  | 6,103 | 6,103 | 2,027 | 0 |

### Statement of financial position

- The draft Statement of Financial Position as of 30 June 2026 is provided below. The main change being the increase in cash and receivables due to the recent completion of the annual billing.

#### Table 4: Statement of financial position

| Statement of financial position | Year to March 26 £'000 | Period to June 2026 £'000 |
| --- | --- | --- |
| Non-current assets |  |  |
| Property, plant and equipment | 38,526 | 36,769 |
| Intangible assets | 6,392 | 6,300 |
| Assets under construction | 1,580 | 1,580 |
| Employee retirement benefits | 0 | 0 |
| Trade and other receivables | 86 | 86 |
| Total non-current assets | 46,584 | 44,735 |
| Current assets |  |  |
| Trade and other receivables | 7,501 | 29,278 |
| Cash and cash equivalents | 4,275 | 22,441 |
| Total current assets | 11,776 | 51,719 |
| Total assets | 58,360 | 96,454 |
| Current liabilities |  |  |
| Trade and other payables | (16,752) | (7,106) |
| Provisions | (881) | (881) |
| Future lease payments | (1,056) | (690) |
| Total current liabilities | (18,689) | (8,677) |
| Total assets less current liabilities | 39,671 | 87,777 |
| Non-current liabilities |  |  |
| Provisions for liabilities and charges >1 year | (4,348) | (4,348) |
| Future lease payments | (3,539) | (3,539) |
| Total non-current liabilities | (7,887) | (7,887) |
| Total assets less total liabilities | 31,784 | 79,890 |
| Taxpayers' equity and other reserves |  |  |
| General fund | 12,562 | 60,668 |
| Revaluation reserve | 19,222 | 19,222 |
| Total taxpayers' equity | 31,784 | 79,890 |

### Recommendation

  - The Board is asked to note SEPA’s financial performance for the period ending 30 June 2026.

END

<Report date here (month, year)>